## Overview
PROPOSAL: ENTERPRISE OMNICHANNEL COMMERCE & FULFILLMENT PLATFORM
Client: NovaRetail Holdings Pty Ltd ¦ Proposal ID: PRP-2026-NOV-01 ¦ Date: 08 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | NovaRetail Holdings Pty Ltd | Presale Solution Lead | Alexandre Martin (Principal Solutions Architect)
Project Code | PBL6-NOVA-OMS-2026 | Delivery Manager | Sarah Jenkins (Senior Agile Delivery Lead)
Proposal Version | v1.0 (Commercial & Technical Bid) | Target Kick-off | 02 November 2026
Primary Objective | Deploy Cloud OMS, Real-Time Inventory, and WMS Lite across 120 Stores & 3 Central Warehouses | Total Delivery Duration | 24 Calendar Weeks (12 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | NovaRetail faces severe revenue leakage due to 4-12 hour inventory sync lags between Shopify Plus, physical store POS systems, and regional warehouses. Inefficient order routing inflates fulfillment costs to $14/order and causes 2.8% fulfillment mis-picks with paper manifests.
Proposed Strategic Solution | We propose delivering a modern, cloud-native Omnichannel Fulfillment Suite ('NovaSync OMS & WMS'). The platform provides a sub-second distributed inventory ledger, intelligent rule-based order routing, mobile handheld PDA warehouse picking, express Click & Collect store workflows, and unified courier label dispatch.
Measurable Business Impact | • 99.8% reduction in cross-channel overselling & stockout cancellations. • 40% reduction in warehouse picking labor hours via digital batch routing. • $4.80 average logistics cost reduction per order via ship-from-nearest-store routing. • Click & Collect turnaround reduced from 25 minutes down to < 45 seconds at store checkout.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $198,500 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $19,850 | Payment Term Milestone Structure | 5 Deliverable-Based Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $218,350 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,800/month (99.9% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Clear division of responsibilities, governance structure, and RACI Matrix across project lifecycle.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
Solution Architect (SA) | Vendor | Part-Time (35%) | Technical architecture governance, system integration design, security compliance, ADR approval | Architecture Blueprint, Integration Specs, Cloud Sizing | Principal
Project Manager (PM) | Vendor | Full-Time (100%) | Agile sprint orchestration, budget & risk tracking, client communication, milestone sign-off | Sprint Burndown, Weekly Status Reports, Risk Log | Senior
Technical Lead (TL) | Vendor | Full-Time (100%) | Codebase stewardship, code review quality gate, tech mentoring, sprint backlog technical grooming | Core Framework Setup, CI/CD Pipeline, DB Schema | Lead
Senior Backend Engineer (2) | Vendor | Full-Time (200%) | Development of OMS routing microservices, real-time inventory locks, SAP & Shopify API connectors | REST/GraphQL APIs, Kafka Consumers, Worker Jobs | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | Next.js 15 Web Portal for operations, store managers, and executive order monitoring dashboard | Responsive Web Portal, Real-time WebSockets Dashboard | Senior
Senior Mobile / PDA Engineer | Vendor | Full-Time (100%) | Flutter cross-platform app for warehouse Zebra handheld scanners and store associate Click & Collect | Zebra PDA APK, Store iOS/Android Associate App | Senior
QA / Automation Lead | Vendor | Full-Time (100%) | Test strategy, automated integration test suites, load testing, regression testing, UAT coordination | Test Plan, Automated E2E Cypress/Postman Suites | Senior
UI/UX Product Designer | Vendor | Phase 1 & 2 (50%) | User journey mapping, warehouse ergonomic UI design, store associate workflow design, design system | Figma Interactive Prototypes, Design System Tokens | Senior
DevOps / Cloud Engineer | Vendor | Part-Time (40%) | AWS infrastructure as code (Terraform), Kubernetes cluster orchestration, monitoring & telemetry | Terraform Scripts, Datadog / Grafana Dashboards | Senior
Product Owner (PO) | Client | Key Stakeholder (40%) | Business requirement clarification, prioritization of user stories, acceptance criteria sign-off | Business Requirements Document (BRD), UAT Sign-off | Executive
Enterprise IT Lead | Client | Key Partner (25%) | Provisioning SAP OData endpoints, firewall whitelist, AWS account IAM role delegation | Enterprise API Credentials, Sandbox Environments | Lead
Retail Operations Champion | Client | Advisory (20%) | Operational input on store workflows, pilot store coordination (Byron & Sydney), staff training | Store Standard Operating Procedures (SOP) | Specialist

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, communication cadence, quality assurance governance, and risk control.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint (Total of 12 Sprints across 24 weeks).
Sprint Planning | Conducted alternate Mondays (9:00 AM - 11:00 AM). User stories estimated using Fibonacci story points.
Daily Standup | 15-minute daily synchronization at 9:30 AM via Slack Huddle / Google Meet. Three questions: What was done yesterday, what will be done today, any blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional software demonstration in Staging environment with client PO and key stakeholders.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Internal vendor team review focusing on process optimization, velocity calibration, and impediments.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts, and Velocity metrics.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specifications, Meeting minutes, Deployment runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, Pull Request peer review requirements (2 approvals), Automated GitHub Actions.
UI/UX Design Collaboration | Figma – Design systems, component libraries, responsive viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#novasync-daily, #novasync-tech-dev, #novasync-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every Pull Request requires 2 peer approvals (including Tech Lead). PR template enforces unit test coverage, security checks, and lint clean.
Automated Test Gates | CI pipeline runs SonarQube quality gate: 0 critical vulnerabilities, < 3% code duplication, minimum 80% automated unit test coverage.
Deployment Automation | Automated deployment to Dev environment on merge to 'develop' branch; Automated Staging deployment on tagged sprint release.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement alteration exceeding 10% deviation from baseline Functional Requirements (FR) sheet.
Impact Assessment | Vendor PM and Solution Architect evaluate impact on budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document detailing added story points, timeline impact, and cost signed off by Client Sponsor prior to implementation.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously during weekly governance meetings.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Shopify Plus GraphQL API rate limits exceeded during flash sales / peak traffic events. | High | Medium | Implement Redis queue buffer with exponential backoff and batch inventory update mutations (max 250 items/call). | Tech Lead
RSK-02 | Risk | Legacy POS batch synchronization latency creates phantom inventory reservations. | High | High | Enforce safety stock buffer threshold (reserve 2 units) and webhook triggers from POS cash register terminals. | Solution Architect
RSK-03 | Risk | Warehouse staff resist transition from paper picking manifests to Android Zebra PDAs. | Medium | High | Conduct comprehensive on-site training sessions in Sydney DC; design high-contrast tactile barcode scanning UX. | Retail Ops Lead
RSK-04 | Risk | Courier carrier API response latency (> 3s) stalls shipping label printing at packing stations. | High | Medium | Pre-fetch courier labels asynchronously during picking phase; cache shipping manifests locally. | Senior Backend
ASM-01 | Assumption | Client Product Owner will be available at least 15 hours/week for sprint ceremonies and prompt UAT sign-off. | High | N/A | Agreed in Project Charter; PO backup appointed (Elena Rostova - COO). | Client Sponsor
ASM-02 | Assumption | Test sandbox credentials for SAP S/4HANA OData services provided no later than Sprint 1 kickoff. | High | N/A | Client IT team confirmed sandbox ready by Oct 28. | Enterprise IT Lead
ASM-03 | Assumption | All 3 Distribution Centers have high-density 5GHz Wi-Fi coverage across all warehouse aisles. | Medium | N/A | Client facility manager conducted RF signal audit in Sept 2026. | Client PM
ISS-01 | Issue | Legacy POS hardware at 18 regional stores has outdated firmware not supporting TLS 1.3. | Medium | Active | Client IT to perform automated overnight firmware update across store POS terminals before Sprint 6. | Enterprise IT Lead
DEP-01 | Dependency | AWS Australia (ap-southeast-2) Production Cloud Account provisioning and enterprise billing activation. | High | Open | DevOps engineer provided Terraform Cloud account requirements; client to sign AWS agreement by Sprint 0. | DevOps Lead
DEP-02 | Dependency | AusPost eParcel and DHL Express commercial API production credentials and contract sign-off. | High | Open | Client Logistics manager managing courier onboarding; mock sandbox services used in Sprints 2-4. | Client Logistics Lead
DEP-03 | Dependency | Zebra TC52 Android handheld scanner hardware procurement and OS staging (120 units total). | Medium | Open | Hardware vendor PO placed; delivery scheduled in two batches (Batch 1: Week 8, Batch 2: Week 14). | Retail Ops Lead

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Milestone acceptance definitions, Definition of Done (DoD), and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed automated linter, and approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass on GitHub Actions.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging environment with database migration scripts verified and idempotency confirmed.
Criterion 5: Documentation | API documentation generated via Swagger / OpenAPI. Any architectural changes documented in Confluence ADR.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story against Gherkin Given-When-Then criteria in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/picking. | Inventory lock engine crashes; all order routing ceases across all stores. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff. | Zebra PDA scanner app crashes when scanning multi-SKU barcode bins. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Courier tracking SMS fails to trigger; customer still receives email update. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across OMS, Real-time Inventory, WMS Lite, Store Associate App & Logistics.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-OMS-01 | Core OMS Engine | Order Ingestion Webhooks | System shall ingest orders in real-time from Shopify Plus, TikTok Shop, and wholesale B2B via secure webhooks. | Must-Have | Medium | Sprint 1
FR-OMS-02 | Core OMS Engine | Intelligent Order Routing | System shall dynamically route orders to the closest fulfillment node (DC or local store) based on distance, stock depth, and carrier cost. | Must-Have | High | Sprint 2
FR-OMS-03 | Core OMS Engine | Split-Shipment Optimization | System shall automatically calculate optimal order splits when a single node cannot fulfill all line items, minimizing shipping legs. | Should-Have | High | Sprint 3
FR-OMS-04 | Core OMS Engine | Order Lifecycle State Machine | System shall maintain finite state machine for orders (Pending, Routed, Allocated, Picking, Shipped, Delivered, Cancelled, Returned). | Must-Have | Medium | Sprint 2
FR-INV-01 | Inventory Engine | Distributed Stock Ledger | System shall maintain an atomic distributed inventory ledger with sub-second balance updates across 120 stores and 3 DCs. | Must-Have | High | Sprint 1
FR-INV-02 | Inventory Engine | Channel Reservation Locks | System shall acquire Redis-backed temporary reservation locks (15 min lease) during online checkout to eliminate overselling. | Must-Have | High | Sprint 2
FR-INV-03 | Inventory Engine | Safety Buffer Rules | System shall allow setting configurable safety stock thresholds per SKU/category (e.g., reserve 2 units for walk-in store customers). | Must-Have | Medium | Sprint 3
FR-INV-04 | Inventory Engine | SAP S/4HANA Reconciliation | System shall execute daily automated two-way inventory reconciliation with SAP Master Inventory, flagging discrepancies. | Should-Have | Medium | Sprint 4
FR-WMS-01 | WMS Lite (DC) | Digital Wave Picking | System shall group orders into optimized pick waves based on warehouse zone, aisle location, and shipping cut-off time. | Must-Have | High | Sprint 5
FR-WMS-02 | WMS Lite (DC) | PDA Barcode Verification | Warehouse pickers using Zebra PDAs shall scan bin barcode and SKU barcode with audible/tactile validation to prevent mis-picks. | Must-Have | Medium | Sprint 5
FR-WMS-03 | WMS Lite (DC) | Packing & Weigh Scale API | Packing station terminal shall integrate with USB digital scale to verify parcel weight against expected SKU weight tolerance. | Should-Have | Medium | Sprint 6
FR-WMS-04 | WMS Lite (DC) | Automated Label Printing | System shall automatically print carrier thermal labels (ZPL format) upon final parcel carton sealing. | Must-Have | Medium | Sprint 6
FR-STR-01 | Store Associate App | Express Click & Collect (BOPIS) | Store associate app shall notify staff of new pickup orders, guide item retrieval in store, and trigger customer ready SMS. | Must-Have | High | Sprint 7
FR-STR-02 | Store Associate App | Fast Customer Pickup Handover | Associate shall scan customer QR code at pickup counter to finalize handover and mark order collected within 15 seconds. | Must-Have | Medium | Sprint 7
FR-STR-03 | Store Associate App | Ship-from-Store Dispatch | Store staff shall receive packing assignments for local courier delivery during store quiet hours, generating courier labels. | Should-Have | High | Sprint 8
FR-LOG-01 | Carrier Logistics Hub | Multi-Carrier Rate Shopping | System shall query AusPost, StarTrack, and DHL Express APIs in parallel to select the cheapest carrier meeting delivery SLA. | Should-Have | Medium | Sprint 8
FR-LOG-02 | Carrier Logistics Hub | Unified Tracking Webhooks | System shall normalize carrier milestone tracking events into unified customer-facing status updates via SMS and email. | Must-Have | Medium | Sprint 9
FR-RPT-01 | Executive Analytics | Live Fulfillment Operations Wallboard | Executive web portal shall display live map of orders, regional stockout heatmaps, picking throughput, and courier SLA compliance. | Must-Have | Medium | Sprint 9
FR-RPT-02 | Executive Analytics | Overselling & Discrepancy Reports | System shall provide automated daily exception reports detailing cancelled orders, stockout causes, and discrepancy root cause. | Should-Have | Low | Sprint 10

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Cloud-native, event-driven, high-throughput microservices architecture hosted on AWS Australia.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Frontend Web Portal | Next.js 15 (React 19, TypeScript) | 15.0+ | Server-Side Rendering (SSR) for fast initial loads, React Server Components for dashboards, built-in security headers. | Open Source (MIT) / Vercel/AWS | Multi-AZ CloudFront CDN
Mobile & PDA Client | Flutter 3.x (Dart) | 3.24+ | Single unified codebase compiling natively to Android (Zebra TC52 PDAs) and iOS (store manager iPhones). 60fps hardware scanning. | Open Source (BSD) / Native | Local SQLite offline cache
Core Backend API | NestJS (Node.js Enterprise) | 10.4+ | Modular TypeScript framework, dependency injection, high developer velocity, native OpenAPI/Swagger generation. | Open Source (MIT) / AWS EKS | Auto-scaling Pods (3-15)
High-Speed Inventory Lock | Go (Golang Microservice) | 1.23+ | Ultra-low memory footprint, goroutine concurrency handling 10,000+ lock leases/sec with sub-5ms response time. | Open Source (BSD) / AWS EKS | Horizontal Auto-scaler
Primary Database | PostgreSQL (AWS Aurora) | 16.x | ACID transactional compliance, JSONB document support for complex order manifests, read-replica scaling. | AWS Managed Aurora PostgreSQL | Multi-AZ Auto-Failover (<30s)
Distributed Cache & Locks | Redis Enterprise (AWS ElastiCache) | 7.2+ | In-memory key-value caching, Redis distributed lock manager (Redlock algorithm) for stock reservation. | AWS Managed ElastiCache | Multi-AZ Cluster Mode
Search & Analytics | Elasticsearch (OpenSearch) | 2.14+ | Sub-50ms full-text search across 50,000 SKUs and historical orders; complex aggregation for dashboard. | AWS OpenSearch Service | 3-Node Master/Data Cluster
Event Streaming & Messaging | Apache Kafka (AWS MSK) / RabbitMQ | 3.7+ | Decoupled asynchronous event pipeline for order events (OrderCreated, StockDeducted, LabelGenerated). | AWS Managed Streaming Kafka | Multi-AZ Topic Replication
Cloud Infrastructure | AWS (Sydney ap-southeast-2) | N/A | Complies with Australian Data Sovereignty; low latency (< 15ms) to physical stores across Sydney & Melbourne. | AWS Cloud Enterprise | Multi-AZ (3 Availability Zones)
DevOps & Orchestration | Terraform & GitHub Actions | 1.9+ | 100% Infrastructure-as-Code (IaC) reproducible environments; automated blue/green zero-downtime deployment. | Open Source / GitHub SaaS | Redundant CI Runners
API Security & Identity | Keycloak / AWS Cognito & OAuth2 | 24.x | Role-Based Access Control (RBAC), OpenID Connect, JWT token expiration with refresh rotation, MFA for managers. | Open Source / AWS | Redundant Auth Servers

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, scalability, and disaster recovery standards.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | API Response Latency | P95 response time < 200ms; P99 response time < 500ms under standard operational load. | Automated k6 load test simulating 1,500 requests/sec. | Redis caching, Aurora DB indexing, lightweight Go microservice for inventory. | Sprint 11 (Load Test)
NFR-PERF-02 | Throughput Scalability | Support 500 peak transactions per second (TPS) during Flash Sale / Black Friday peaks. | Distributed load test simulating 35,000 orders over 1-hour burst. | AWS EKS Horizontal Pod Autoscaler (HPA) and SQS/Kafka decoupling. | Sprint 11 (Load Test)
NFR-AVAIL-01 | System Availability | 99.95% uptime availability (<= 21.6 minutes unscheduled downtime per calendar month). | Datadog synthetic uptime monitoring from 5 global locations. | Multi-AZ AWS deployment with active health-check auto-healing pods. | Production Go-Live
NFR-SEC-01 | Data Encryption | AES-256 encryption at rest for all databases/backups; TLS 1.3 in transit with HSTS enforced. | AWS Security Hub automated compliance audit scan. | AWS KMS managed customer master keys (CMK) and SSL certificates. | Sprint 10 (Security)
NFR-SEC-02 | Authentication & Access | Role-Based Access Control (RBAC) with OAuth2 / JWT; Multi-Factor Authentication (MFA) for Admin. | Penetration test report by CREST-certified security auditor. | Strict Spring/NestJS guard middleware and Keycloak policy enforcement. | Sprint 11 (Pentest)
NFR-SEC-03 | Compliance Sovereignty | All customer Personally Identifiable Information (PII) hosted in Australia (ap-southeast-2). | Independent cloud architecture data residency audit. | AWS IAM geographical SCP policies preventing non-Australian region spins. | Sprint 10 (Security)
NFR-DR-01 | Disaster Recovery (RPO) | Recovery Point Objective (RPO) < 5 minutes (maximum 5 minutes of transactional data loss). | Quarterly disaster recovery tabletop simulation drill. | Aurora continuous incremental storage backup and S3 cross-region sync. | Pre-Go-Live Drill
NFR-DR-02 | Disaster Recovery (RTO) | Recovery Time Objective (RTO) < 30 minutes to restore full transactional capabilities. | Automated Terraform failover spin-up verification test. | Infrastructure-as-Code Terraform deployment scripts stored in GitHub. | Pre-Go-Live Drill
NFR-OBS-01 | Observability & Tracing | 100% distributed trace capture for order lifecycle with centralized log retention (365 days). | OpenTelemetry distributed trace sampling verification. | Datadog APM / AWS CloudWatch Logs with automated P1 Slack alerting. | Sprint 9

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role. Currency: USD (ex GST/Tax). Standard day = 8 productive hours.
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ years enterprise software architecture, cloud certification (AWS Pro)
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ years managing Agile software projects, PMP / PMI-ACP certified
Technical Lead | Lead | 75 | 600 | 3000 | 10+ years backend & distributed systems, architecture governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ years Node.js, Go, PostgreSQL, high-throughput microservices
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ years React, Next.js, modern CSS, enterprise dashboard UX
Senior Mobile / PDA Engineer | Senior | 60 | 480 | 2400 | 6+ years Flutter/Android, hardware barcode integration (Zebra EMDK)
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ years test automation, Cypress, Postman, performance k6 testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ years design systems, mobile ergonomics, retail workflow design
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ years AWS, Kubernetes (EKS), Terraform, CI/CD pipeline automation
Business Analyst | Senior | 55 | 440 | 2200 | 6+ years retail supply chain, functional requirement specification
Mid-Level Software Engineer | Mid | 42.5 | 340 | 1700 | 3-5 years full-stack development, API integration, unit testing

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline breakdown, Work Breakdown Structure (WBS), Quotation summary, and Milestone Payment Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (24 WEEKS / 12 SPRINTS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & UX Design | Week 1 | 3 Weeks | Discovery workshops, architecture blueprint, DB schema design, Zebra PDA ergonomic UI prototypes, AWS environment setup. | Solution Architecture Document, Interactive Figma Prototype, Sprint Backlog | Milestone 1 Sign-off
Phase 2 | Core OMS & Inventory Ledger Engine | Week 4 | 8 Weeks | Develop sub-second inventory engine, Shopify Plus webhooks, Redis reservation locks, SAP OData reconciliation, core routing engine. | OMS Core Services in Staging, Automated API Test Suite, Inventory Lock Engine Demo | Milestone 2 Sign-off
Phase 3 | WMS Lite, Store App & Courier Hub | Week 12 | 7 Weeks | Develop Zebra PDA scanner wave picking app, store Click & Collect associate app, carrier rating & ZPL thermal label printer integration. | Android PDA Build, Store Associate App, Courier Hub Connector Suite | Milestone 3 Sign-off
Phase 4 | System Integration, UAT & Pentest | Week 19 | 3 Weeks | End-to-end integration testing, business user UAT in simulated store/DC, k6 load testing (500 TPS), independent CREST security pentest. | UAT Acceptance Certificate, Penetration Test Report, Load Test Benchmark Report | Milestone 4 Sign-off
Phase 5 | Production Pilot, Rollout & Hypercare | Week 22 | 3 Weeks | Production deployment on AWS EKS, Pilot go-live across Sydney DC & 10 flagship stores, staff training, 24/7 on-site hypercare. | Production Handover Runbook, Staff Training Material, Final Acceptance Certificate | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & UI/UX Prototypes | 45 | 633.33 | 28500 | SA (12d), PM (8d), TL (10d), UI/UX (15d) | Fixed Milestone
WBS-02 | Phase 2: Core OMS, Inventory Ledger & SAP/Shopify Sync | 140 | 520 | 72800 | Backend (60d), Tech Lead (30d), PM (20d), QA (20d), DevOps (10d) | Fixed Milestone
WBS-03 | Phase 3: WMS Scanner App, Store BOPIS App & Logistics Hub | 110 | 496.36 | 54600 | Mobile (40d), Frontend (30d), Backend (20d), QA (20d) | Fixed Milestone
WBS-04 | Phase 4: End-to-End Testing, Security Pentest & UAT | 50 | 492 | 24600 | QA Lead (25d), PM (10d), SA (5d), Security/DevOps (10d) | Fixed Milestone
WBS-05 | Phase 5: Production Deployment, Pilot Rollout & Hypercare | 36 | 500 | 18000 | Tech Lead (12d), PM (12d), Mobile (6d), Backend (6d) | Fixed Milestone
Subtotal Professional Services (381 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Inception Kick-off | 20% | 43670 | Nov 02, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Architecture Sign-off & Core OMS Staging Demo | 25% | 54587.5 | Dec 21, 2026 (End Sprint 3) | Due within 14 days of gate approval
Milestone 3 | Feature Complete: WMS Scanner & Store App Release | 30% | 65505 | Feb 22, 2027 (End Sprint 8) | Due within 14 days of gate approval
Milestone 4 | UAT Sign-off & Pilot Go-Live (Sydney DC + 10 Stores) | 15% | 32752.5 | Mar 29, 2027 (End Sprint 10) | Due within 14 days of gate approval
Milestone 5 | Final Handover & 90-Day Hypercare Acceptance | 10% | 21835 | Apr 19, 2027 (Final Gate) | Due within 30 days of sign-off