## Overview
HOTEL PMS (SaaS) PROPOSAL
Client | Coastal Stay Hotels Pty Ltd
Project | Cloud Hotel PMS (SaaS) – 3 properties
Proposal ID | PRP-PMS-2026-002
Date | 2026-10-08
Presale lead | Presale A
Valid for (days) | 30
SUMMARY
Properties | 3
Total rooms | 220
Subscription Year 1 (AUD ex GST) | 49200
One-off services, net (AUD ex GST) | 117117
Total Year 1 (AUD ex GST) | 173697
Total Year 1 (AUD inc GST) | 191066.7
3-year total (AUD ex GST) | 292000.122
Implementation duration (weeks) | 26
WHY THIS SOLUTION
• One cloud PMS across all three hotels, no on-site servers to maintain.
• Two-way channel manager removes double bookings and manual rate updates.
• Mobile housekeeping and automated night audit save daily staff time.
• Group dashboard gives head office live numbers across every property.
• Phased roll-out starting with a pilot hotel and avoiding the peak season.
See sheets: Scope, Pricing, Timeline, Terms. Change inputs in the Inputs sheet and everything updates.

## Inputs
INPUTS (blue text / yellow fill = editable)
Parameter | Value
Client | Coastal Stay Hotels Pty Ltd
Project | Cloud Hotel PMS (SaaS) – 3 properties
Proposal ID | PRP-PMS-2026-002
Proposal date | 2026-10-08
Valid for (days) | 30
Presale lead | Presale A
Day rate (AUD ex GST) | 1300
GST rate | 10%
Implementation discount | 10%
Premium support (% of annual subscription) | 15%
Services contingency (% of B + C) | 10%
Annual price increase cap (CPI assumption) | 3%
Subscription term (months, per year) | 12
Day rate, subscription prices, discount and support % are presale assumptions for illustration. Confirm with Sales/Finance before sending.

## Scope
SCOPE
1. Properties
# | Property | Location | Rooms | Go-live wave
1 | Byron Bay | NSW | 48 | Wave 1 (pilot)
2 | Gold Coast | QLD | 112 | Wave 2
3 | Sydney CBD | NSW | 60 | Wave 3
| Total rooms |  | 220
2. Subscription modules
# | Module | Key capabilities
1 | Core PMS | Reservations, front desk, folios and billing, rate plans, night audit, GST handling
2 | Housekeeping & Maintenance | Mobile room status, task allocation, maintenance tickets, lost property
3 | Channel Manager | Two-way sync with Booking.com, Expedia and Airbnb: rates, availability, reservations
4 | Direct Booking Engine | Website booking widget, packages and promo codes, payments
5 | Revenue & Reporting | Occupancy, ADR, RevPAR, pickup, budget vs actual, scheduled reports
6 | Guest CRM & Messaging | Guest profiles, preferences, automated pre-arrival and post-stay emails/SMS
7 | Group Dashboard (HQ) | Consolidated view across all properties, user roles and permissions
3. Integrations in scope
1 | Channel manager connections (Booking.com, Expedia, Airbnb)
2 | Payments: Stripe (all properties), Tyro (Gold Coast restaurant)
3 | Accounting: Xero
4 | Restaurant POS (Gold Coast)
5 | Door locks: Salto
6 | Website booking engine embed

## Pricing
PRICING (AUD, excluding GST unless stated)
Blue = assumption, green = linked from another sheet, black = formula.
A. SaaS SUBSCRIPTION (Year 1)
# | Module | Unit | Qty | Price / unit / month | Months | Annual amount
1 | Core PMS | room / month | 220 | 9 | 12 | 23760
2 | Housekeeping & Maintenance | room / month | 220 | 2 | 12 | 5280
3 | Channel Manager | room / month | 220 | 2.5 | 12 | 6600
4 | Direct Booking Engine | room / month | 220 | 1.5 | 12 | 3960
5 | Revenue & Reporting | room / month | 220 | 1.5 | 12 | 3960
6 | Guest CRM & Messaging | room / month | 220 | 1 | 12 | 2640
7 | Group Dashboard (HQ) | flat / month | 1 | 250 | 12 | 3000
| Total A – Subscription |  |  |  |  | 49200
B. IMPLEMENTATION SERVICES
# | Item | Unit | Days | Day rate |  | Amount
1 | Project management | day | 15 | 1300 |  | 19500
2 | Discovery & solution design workshops | day | 6 | 1300 |  | 7800
3 | System configuration (rooms, rates, taxes, packages, users) | day | 12 | 1300 |  | 15600
4 | Data migration (guest profiles, future reservations) | day | 10 | 1300 |  | 13000
5 | Staff training (on site, per property) | day | 8 | 1300 |  | 10400
6 | Go-live support (hypercare) | day | 8 | 1300 |  | 10400
| Total B – Implementation |  | 59 |  |  | 76700
C. INTEGRATIONS
# | Item | Unit | Days | Day rate |  | Amount
1 | Channel manager (Booking.com, Expedia, Airbnb) | day | 6 | 1300 |  | 7800
2 | Payments (Stripe, Tyro) | day | 5 | 1300 |  | 6500
3 | Accounting (Xero) | day | 5 | 1300 |  | 6500
4 | Restaurant POS (Gold Coast) | day | 7 | 1300 |  | 9100
5 | Door locks (Salto) | day | 6 | 1300 |  | 7800
6 | Website booking engine embed | day | 3 | 1300 |  | 3900
| Total C – Integrations |  | 32 |  |  | 41600
D. SUPPORT & CONTINGENCY
# | Item | Unit | Rate | Base |  | Amount
1 | Premium support (24/7 urgent, Year 1) | % of A | 15% | 49200 |  | 7380
2 | Services contingency | % of B + C | 10% | 118300 |  | 11830
YEAR 1 SUMMARY
| One-off services before discount (B + C + contingency) |  |  |  |  | 130130
| Implementation discount |  |  |  |  | -13013
| One-off services, net |  |  |  |  | 117117
| Subscription, Year 1 (A) |  |  |  |  | 49200
| Premium support, Year 1 |  |  |  |  | 7380
| TOTAL YEAR 1 (ex GST) |  |  |  |  | 173697
| GST |  |  |  |  | 17369.7
| TOTAL YEAR 1 (inc GST) |  |  |  |  | 191066.7
3-YEAR COST OUTLOOK (ex GST)
|  |  | Year 1 | Year 2 | Year 3 | 3-year total
| Subscription (price increases at CPI cap from Year 2) |  | 49200 | 50676 | 52196.28 | 152072.28
| Premium support |  | 7380 | 7601.4 | 7829.442 | 22810.842
| One-off services, net (Year 1 only) |  | 117117 | 0 | 0 | 117117
| Total (ex GST) |  | 173697 | 58277.4 | 60025.722 | 292000.122
| Total (inc GST) |  | 191066.7 | 64105.14 | 66028.2942 | 321200.1342

## Timeline
IMPLEMENTATION TIMELINE (weeks)
Phase | Activities | Start (week) | Duration (weeks) | End (week)
Discovery & design | Kick-off, workshops, rate and room setup design | 1 | 3 | 3
Build & integrations | Configuration, channel manager, payments, Xero, POS, door locks | 4 | 8 | 11
Wave 1 – Byron Bay | Data migration, UAT, training, go-live (pilot) | 10 | 5 | 14
Wave 2 – Gold Coast | Migration, UAT, training, go-live | 15 | 4 | 18
Wave 3 – Sydney CBD | Migration, UAT, training, go-live | 19 | 4 | 22
Hypercare & handover | Stabilisation, final training, transition to support | 23 | 4 | 26
Total duration (weeks) |  |  |  | 26
Assumes kick-off in early November 2026. Wave 1 go-live avoids the Christmas–January peak (falls in about February 2027).

## Terms
ASSUMPTIONS, EXCLUSIONS & TERMS
Type | Detail
Assumption | Room counts, module selection and day estimates are initial estimates and will be confirmed after discovery.
Assumption | Client provides a project lead, data exports from the legacy PMS and timely UAT feedback.
Assumption | Subscription is billed monthly; prices shown are per room per month and exclude GST.
Assumption | Customer and payment data is hosted in Australian cloud regions.
Exclusion | Hardware (tablets, key encoders, card terminals) and network upgrades at the properties.
Exclusion | Third-party fees: channel/OTA commissions, payment processing fees, Xero, POS and door lock vendor charges.
Exclusion | Changes in scope after design sign-off, charged at the day rate in the Inputs sheet.
Terms | Suggested payment: 30% on signing, 40% across go-live waves, 30% after hypercare. Subscription starts at first go-live.
Terms | Minimum subscription term and price-increase cap to be confirmed in the contract.
Terms | This quote is valid for the number of days stated in the Inputs sheet.