## Overview
PROPOSAL: NEXT-GEN DIGITAL BANKING & MICRO-LENDING PLATFORM
Client: ApexCredit Financial Technologies Ltd ¦ Proposal ID: PRP-2026-APX-02 ¦ Date: 12 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | ApexCredit Financial Technologies Ltd | Presale Solution Lead | Julianna Ross (Principal FinTech Architect)
Project Code | PBL6-APX-BANK-2026 | Delivery Manager | Marcus Sterling (Senior FinTech Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 09 November 2026
Primary Objective | Deploy Native iOS/Android Banking App, Instant eKYC, and Real-time Lending Engine | Total Delivery Duration | 22 Calendar Weeks (11 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | ApexCredit suffers from 62% customer onboarding abandonment due to 48-hour manual ID checks and spreadsheet underwriting. Lack of native mobile apps and manual reconciliation exposes the company to fraud ($320k last quarter) and brand erosion.
Proposed Strategic Solution | We propose 'ApexCore Digital Bank': A secure, cloud-native FinTech platform comprising high-performance Flutter mobile apps, an automated eKYC pipeline with biometric liveness, algorithmic credit scoring integrating Equifax & Open Banking CDR, and sub-60s NPP/Osko loan disbursement.
Measurable Business Impact | • Onboarding drop-off reduced from 62% down to < 12% via 90-second instant eKYC. • Loan decisioning accelerated from 48 hours to under 60 seconds automated approval. • Synthetic identity fraud reduced by 98% via biometric liveness verification. • Loan book volume capacity increased from 4,500/day to 50,000+ daily applications.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $188,400 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $18,840 | Payment Term Milestone Structure | 5 Deliverable-Based Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $207,240 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $5,200/month (99.99% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
FinTech Solution Architect | Vendor | Part-Time (40%) | Security architecture, APRA CPS 234 compliance, Open Banking & Core banking API design | Security Blueprint, CDR Integration Spec, Threat Model | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint governance, PCI-DSS compliance coordination, budget & timeline management | Burndown Charts, Risk Register, Governance Reports | Senior
Technical Lead | Vendor | Full-Time (100%) | Lead microservice architecture, encryption key management, code review quality gate | Core Architecture, CI/CD, Key Management Framework | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Lending engine, eKYC integration, credit scoring microservice, NPP payment rails | REST/gRPC APIs, Underwriting Engine, Worker Jobs | Senior
Senior Mobile Engineers (2) | Vendor | Full-Time (200%) | Native iOS & Android development in Flutter, biometric security, camera capture | Flutter Banking App, Security Keystore Integration | Senior
QA / Security Test Lead | Vendor | Full-Time (100%) | Automated test suites, security vulnerability testing, financial calculation audits | Test Automation Suite, Financial Audit Report | Senior
UI/UX Product Designer | Vendor | Phase 1 & 2 (50%) | FinTech ergonomics, friction-free onboarding UX, loan repayment visualization | Figma Design System, Interactive Prototypes | Senior
DevOps & Cloud Security | Vendor | Part-Time (40%) | AWS Multi-Region deployment, KMS encryption, WAF, automated security scanning | Terraform Scripts, SOC2 Compliance Infrastructure | Senior
Product Owner (PO) | Client | Key Stakeholder (40%) | Credit risk policy clarification, lending criteria sign-off, regulatory review | Credit Policy Specification, UAT Acceptance | Executive
Chief Risk Officer | Client | Advisory (20%) | Underwriting model validation, bureau integration rules, fraud thresholds | Credit Risk & Underwriting Rulebook | Executive

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Equifax or Illion credit bureau API downtime causes lending decision stalls. | High | Low | Implement dual-bureau failover fallback logic; if Equifax fails, route to Illion automatically. | Tech Lead
RSK-02 | Risk | App Store / Google Play review rejection due to strict financial services lending guidelines. | High | Medium | Prepare legal credit license documentation, APR disclosures, and conduct pre-submission review. | Compliance Lead
RSK-03 | Risk | Open Banking (CDR) user consent friction during bank statement ingestion. | Medium | Medium | Design high-trust bank connection UI with accredited CDR data recipient badge. | UI/UX Designer
ASM-01 | Assumption | Client maintains active Australian Credit Licence (ACL) and DVS bureau credentials. | High | N/A | Client compliance team confirmed licences active and in good standing. | Client Sponsor
DEP-01 | Dependency | NPP / Osko banking partner API sandbox access and settlement escrow account. | High | Open | Client treasury team coordinating with Cuscal / banking partner for sandbox keys. | Client IT
DEP-02 | Dependency | FrankieOne / IDverse eKYC commercial API subscription provisioned by Week 3. | High | Open | Contract execution underway; mock eKYC sandbox used for Sprint 1. | Client PM

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-KYC-01 | Onboarding & eKYC | Biometric Document Verification | System shall capture user photo ID, verify against Australian DVS database, and perform 3D liveness check. | Must-Have | High | Sprint 1
FR-KYC-02 | Onboarding & eKYC | Open Banking CDR Bank Retrieval | System shall securely connect to user bank via CDR and retrieve 90 days of categorised bank statements. | Must-Have | High | Sprint 2
FR-UND-01 | Credit Underwriting | Automated Credit Bureau Pull | System shall query Equifax credit score, default records, and debt-to-income metrics via automated API. | Must-Have | High | Sprint 3
FR-UND-02 | Credit Underwriting | Decisioning Rule Engine | System shall calculate risk grade (A-E), generate instant approval or decline, and set credit limit in <60s. | Must-Have | High | Sprint 3
FR-LOAN-01 | Loan Management | Dynamic Loan Calculator | Mobile app shall provide interactive slider for loan amount ($500-$3,500) and tenure with transparent APR fees. | Must-Have | Medium | Sprint 4
FR-LOAN-02 | Loan Management | Digital Contract E-Sign | System shall generate DocuSign/built-in digital credit contract and record cryptographic timestamp consent. | Must-Have | Medium | Sprint 4
FR-PAY-01 | Payment & Disbursement | Real-Time NPP / Osko Payout | System shall disburse approved loan funds via NPP/Osko within 60 seconds directly to user PayID/BSB. | Must-Have | High | Sprint 5
FR-PAY-02 | Payment & Disbursement | Automated Repayment Debits | System shall execute automated scheduled repayments via PayID and stored debit card with pre-debit SMS. | Must-Have | High | Sprint 6
FR-MOB-01 | Mobile Banking App | Biometric Authentication | Mobile app shall support FaceID, TouchID, and cryptographic device binding with jailbreak detection. | Must-Have | High | Sprint 5
FR-MOB-02 | Mobile Banking App | Repayment Schedule & Early Pay | Mobile app shall display upcoming payment calendar and allow 1-click fee-free early loan payoff. | Must-Have | Medium | Sprint 7
FR-ADM-01 | Backoffice Portal | Underwriting Override & Audit | Backoffice web portal shall allow compliance officers to inspect loan applications and audit trail. | Must-Have | Medium | Sprint 8
FR-ADM-02 | Backoffice Portal | Collections & Arrears Tracker | System shall flag overdue accounts, automate grace-period reminders, and generate regulatory reports. | Should-Have | Medium | Sprint 9

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Mobile Banking App | Flutter 3.x (Dart) | 3.24+ | Single secure codebase with hardware keystore integration, SSL pinning, and jailbreak detection. | Open Source / Native | Redundant CDN endpoints
Core Backend API | Go (Golang) & NestJS | 1.23+ / 10+ | Go for ultra-fast underwriting engine; NestJS for financial ledger domain services. | Open Source / AWS EKS | Auto-scaling Pods (4-20)
Financial Database | PostgreSQL (AWS Aurora) | 16.x | ACID compliance, strict double-entry ledger database schema, encrypted column storage. | AWS Managed Aurora | Multi-AZ Auto-Failover (<20s)
Cache & Lock Service | Redis Enterprise | 7.2+ | In-memory session state, rate-limiting, and idempotency key locks preventing double-spend. | AWS ElastiCache | Multi-AZ Replication
Event Bus | Apache Kafka (AWS MSK) | 3.7+ | Audit-compliant immutable event log for every financial transaction and state change. | AWS Managed Kafka | 3-AZ Cluster
Cloud & Security | AWS Sydney (ap-southeast-2) | N/A | APRA CPS 234 compliant architecture, AWS KMS Hardware Security Module (HSM), CloudHSM. | AWS Enterprise | Multi-AZ (3 Zones)
WAF & DDoS | Cloudflare Enterprise & AWS WAF | N/A | Financial-grade DDoS mitigation, rate-limiting, bot protection, and mTLS API protection. | Cloudflare / AWS | Global Anycast

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Loan Decision Latency | End-to-end automated credit decisioning generated in < 90 seconds (P95) from submission. | Automated performance benchmark with simulated bureau response. | Asynchronous parallel API invocation of bureau & CDR. | Sprint 10
NFR-PERF-02 | Peak Throughput | Handle 2,000 concurrent mobile app users and 200 loan applications/minute. | k6 load test simulating high-volume payday rush. | Go microservice architecture with read-replica DB pool. | Sprint 10
NFR-AVAIL-01 | System Availability | 99.99% core transaction uptime (less than 4.3 minutes unscheduled downtime/month). | Synthetic multi-location health probes with automated failover. | Multi-AZ Aurora, EKS pod autoscaling, multi-node Kafka. | Production Go-Live
NFR-SEC-01 | Encryption Standards | AES-256 for all PII data and database columns; TLS 1.3 with certificate pinning on mobile. | Independent CREST penetration test and cryptographic audit. | AWS KMS Customer Master Keys and Hardware Security Module. | Sprint 9
NFR-SEC-02 | Regulatory Compliance | Full compliance with APRA CPS 234, PCI-DSS Level 1, and Australia Privacy Act 1988. | External compliance audit report by accredited QSA. | Zero plain-text PAN storage, strict RBAC, immutable logs. | Sprint 10

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (22 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & Compliance Blueprint | Week 1 | 3 Weeks | Architecture specifications, APRA compliance model, eKYC & bureau API integration design, Figma UI prototypes. | Architecture Document, Security Blueprint, Figma Prototype | Milestone 1 Sign-off
Phase 2 | Core Lending Engine, eKYC & Bureau Connectors | Week 4 | 7 Weeks | Develop automated eKYC pipeline, Equifax/Illion integration, Open Banking ingestion, risk scoring microservice. | Lending Engine API in Staging, eKYC Demo, Underwriting Suite | Milestone 2 Sign-off
Phase 3 | Mobile Banking Apps & NPP Payment Rails | Week 11 | 6 Weeks | Develop Flutter mobile apps (iOS/Android), NPP/Osko payout rails, PayID repayments, biometric binding. | Flutter App Builds (TestFlight/Play Console), Payout Demo | Milestone 3 Sign-off
Phase 4 | Security Pentest, Load Testing & UAT | Week 17 | 3 Weeks | External CREST security penetration testing, PCI-DSS compliance verification, financial math audits, UAT. | Pentest Clearance Report, UAT Acceptance Certificate | Milestone 4 Sign-off
Phase 5 | Production Deployment, App Store Launch & Hypercare | Week 20 | 3 Weeks | App Store / Google Play public release, production cloud cutover, 24/7 on-call engineering hypercare. | Production Verification Sign-off, Final Handover | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & Security Design | 40 | 650 | 26000 | FinTech SA (12d), PM (8d), Tech Lead (10d), UI/UX (10d) | Fixed Milestone
WBS-02 | Phase 2: Lending Engine, eKYC & Bureau Integration | 130 | 526.15 | 68400 | Backend (60d), Tech Lead (25d), PM (15d), QA (20d), DevOps (10d) | Fixed Milestone
WBS-03 | Phase 3: Mobile Apps & NPP Payout Rails | 110 | 510.91 | 56200 | Mobile (50d), Backend (25d), QA (20d), PM (15d) | Fixed Milestone
WBS-04 | Phase 4: Security Pentest, Load Testing & UAT | 48 | 483.33 | 23200 | QA Lead (20d), Security SA (8d), PM (10d), DevOps (10d) | Fixed Milestone
WBS-05 | Phase 5: Production Deployment, App Store Launch & Hypercare | 32 | 456.25 | 14600 | Tech Lead (10d), PM (10d), Mobile (6d), Backend (6d) | Fixed Milestone
Subtotal Professional Services (360 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 41448 | Nov 09, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Lending Engine & eKYC Staging Verification | 25% | 51810 | Dec 28, 2026 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Mobile App Feature Complete & Payout Demo | 30% | 62172 | Feb 08, 2027 (End Sprint 7) | Due within 14 days of gate approval
Milestone 4 | Security Pentest Sign-off & App Store Submission | 15% | 31086 | Mar 15, 2027 (End Sprint 9) | Due within 14 days of gate approval
Milestone 5 | Production Launch & 90-Day Hypercare Acceptance | 10% | 20724 | Apr 05, 2027 (Final Gate) | Due within 30 days of sign-off