## Overview
PROPOSAL: ENTERPRISE CLOUD EHR & TELEHEALTH PLATFORM
Client: MediCare Regional Health Network ¦ Proposal ID: PRP-2026-MED-03 ¦ Date: 16 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | MediCare Regional Health Network | Presale Solution Lead | Dr. Alistair Chen (Chief Clinical Architect)
Project Code | PBL6-MED-EHR-2026 | Delivery Manager | Fiona Gallagher (Senior HealthTech Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial Bid) | Target Kick-off | 16 November 2026
Primary Objective | Deploy Unified Cloud EHR, Patient Portal, and Telehealth across 14 Regional Clinics | Total Delivery Duration | 24 Calendar Weeks (12 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | MediCare suffers from fragmented on-premise clinic servers, 18% appointment no-show rates ($450k lost revenue), 45-minute waiting room congestion, and clinical risks due to lack of cross-clinic medical record visibility.
Proposed Strategic Solution | We propose delivering 'MediSync Health Cloud': A unified cloud EHR platform featuring a centralized longitudinal patient health record, digital mobile patient intake, WebRTC secure video telehealth, automated SMS reminders, and Australian eRx / Medicare integration.
Measurable Business Impact | • 75% reduction in appointment no-show rates (from 18% down to < 4.5%) via automated two-way SMS. • Waiting room check-in time slashed from 45 minutes to < 3 minutes via mobile pre-intake. • $180k annual savings from eliminating duplicate pathology testing across network clinics. • 100% elimination of on-premise clinic server failure risks through secure AWS Sydney hosting.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $196,250 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $19,625 | Payment Term Milestone Structure | 5 Deliverable-Based Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $215,875 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,900/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
HealthTech Solution Architect | Vendor | Part-Time (35%) | Clinical architecture, HL7/FHIR interoperability, My Health Record security governance | EHR Architecture Blueprint, FHIR Data Model, Security Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Clinical sprint orchestration, clinic staff rollout planning, regulatory milestone sign-off | Sprint Burndown, Clinical Training Plan, Status Reports | Senior
Technical Lead | Vendor | Full-Time (100%) | Lead microservices engineering, HL7 integration engine, cryptographic audit trail | Core Framework, CI/CD, FHIR Integration Service | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | EHR patient record services, appointment scheduler, eRx connector, Medicare billing API | REST/FHIR APIs, Clinical Database Schema, Workers | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | Doctor clinical workstation portal (Next.js 15), WebRTC telehealth interface, appointment matrix | Responsive Clinical Web Portal, Telehealth UI | Senior
Senior Mobile Engineer | Vendor | Full-Time (100%) | Patient mobile portal (Flutter) for appointment booking, test results, and check-in | iOS & Android Patient App Builds | Senior
QA / Clinical Systems Lead | Vendor | Full-Time (100%) | Clinical workflow test suites, drug-allergy interaction verification, HL7 message testing | Automated Clinical Test Suite, RACGP Audit Report | Senior
UI/UX Product Designer | Vendor | Phase 1 & 2 (50%) | High-efficiency doctor charting ergonomics, patient mobile accessibility design | Figma Design System, Doctor Charting Wireframes | Senior
DevOps & Cloud Security | Vendor | Part-Time (40%) | AWS Sydney health-grade deployment, KMS encryption, automated disaster recovery | Terraform Scripts, Health Cloud Infrastructure | Senior
Product Owner (PO) | Client | Key Stakeholder (40%) | Clinical requirement clarification, medical specialty charting input, UAT sign-off | Clinical Requirements Specification, UAT Sign-off | Executive
Director of Health Informatics | Client | Key Partner (25%) | Legacy database export coordination, clinic network firewall whitelist, My Health Record liaison | Legacy Database Exports, Clinic IT Liaison | Lead

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Doctor resistance to adopting new electronic charting interface during busy clinic days. | High | High | Engage clinical champions; design ultra-fast keyboard shortcuts and 1-click charting templates. | Clinical Architect
RSK-02 | Risk | Corrupted or non-standard clinical data in legacy 2012 on-premise database exports. | High | Medium | Run automated data cleansing and deduplication scripts during Phase 2; clinical validation audit. | Tech Lead
RSK-03 | Risk | Services Australia Medicare claiming API gateway latency or certification delays. | High | Low | Initiate Medicare vendor software integration testing early in Sprint 2. | Lead Backend
ASM-01 | Assumption | Client clinic rooms have stable 50+ Mbps fiber internet connection for HD video telehealth. | Medium | N/A | Client IT confirmed all 14 clinics upgraded to NBN Enterprise Ethernet. | Client IT
DEP-01 | Dependency | Australian eRx Script Exchange vendor production credentials and test certificate. | High | Open | Client medical director submitted eRx agreement; sandbox keys delivered. | Client Sponsor

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-EHR-01 | Clinical Record | Longitudinal Patient Record | System shall display consolidated medical history, previous consultations, vitals, and allergies in single view. | Must-Have | High | Sprint 1
FR-EHR-02 | Clinical Record | Drug-Allergy Interaction Engine | System shall automatically check proposed prescriptions against patient allergy profile and trigger warnings. | Must-Have | High | Sprint 2
FR-SCH-01 | Appointment Engine | Multi-Clinic Doctor Scheduler | System shall manage doctor appointment slots across all 14 clinics with real-time multi-practitioner calendar. | Must-Have | Medium | Sprint 3
FR-SCH-02 | Appointment Engine | Automated Two-Way SMS Reminders | System shall dispatch automated SMS reminders 48h and 24h prior, allowing 1-click confirmation or reschedule. | Must-Have | Medium | Sprint 3
FR-INT-01 | Patient Mobile Intake | Pre-Visit Digital Check-In | Patients shall receive mobile intake link to verify Medicare details, upload insurance, and answer symptoms. | Must-Have | High | Sprint 4
FR-TEL-01 | Telehealth Suite | Encrypted WebRTC Video Consultation | Doctor workstation shall launch embedded peer-to-peer HD video call with patient directly within clinical note tab. | Must-Have | High | Sprint 5
FR-TEL-02 | Telehealth Suite | In-Call Medical Documentation | Doctor shall enter clinical findings, diagnoses (ICD-10/SNOMED CT), and orders during active video session. | Must-Have | Medium | Sprint 6
FR-RX-01 | Prescriptions & Labs | Australian eRx Electronic Scripts | System shall generate legally compliant e-prescriptions with cryptographic QR barcode sent via SMS to patient. | Must-Have | High | Sprint 7
FR-RX-02 | Prescriptions & Labs | HL7 Pathology Lab Ordering | System shall send electronic lab order requests and ingest diagnostic pathology reports via HL7 v2.4 feeds. | Must-Have | High | Sprint 8
FR-BIL-01 | Billing & Claiming | Medicare & DVA Online Claiming | System shall submit direct batch bulk-billing and patient claiming to Medicare Australia API in real-time. | Must-Have | High | Sprint 9
FR-PAT-01 | Patient Mobile Portal | Mobile App Consultation Booking | Patients shall search doctors, book appointments, view upcoming visits, and view test results on mobile. | Must-Have | Medium | Sprint 9

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Doctor Web Workstation | Next.js 15 (React 19, TypeScript) | 15.0+ | Fast server-side rendering, sub-second patient record switching, Tailwind CSS medical UI. | Open Source / AWS | Multi-AZ CloudFront
Patient Mobile App | Flutter 3.x (Dart) | 3.24+ | Single accessible cross-platform app for patients to check in, book appointments, and view e-scripts. | Open Source / Native | Redundant App Gateways
Core Clinical Backend | NestJS (Node.js) & Python FHIR | 10.4+ / 3.12+ | NestJS for microservices; Python for HL7/FHIR parsing and clinical data transformers. | Open Source / AWS EKS | Auto-scaling Pods (3-15)
Telehealth Media Server | LiveKit / WebRTC Cloud | 1.7+ | Low-latency WebRTC media routing, selective forwarding unit (SFU), end-to-end media encryption. | LiveKit Cloud / AWS | Global TURN/STUN cluster
Clinical Database | PostgreSQL (AWS Aurora) | 16.x | ACID compliance, JSONB for flexible medical assessment forms, row-level security for HIPAA compliance. | AWS Managed Aurora | Multi-AZ Auto-Failover (<30s)
Audit Logging & Search | AWS OpenSearch & Redis | 2.14+ / 7.2+ | Full-text medical history search; immutable audit trail recording every medical chart view. | AWS OpenSearch | Multi-Node Cluster
Cloud & Compliance | AWS Sydney (ap-southeast-2) | N/A | Dedicated VPC, HIPAA & Australian Privacy Act compliance, AWS KMS customer-managed keys. | AWS Cloud Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Patient Chart Loading Time | Complete longitudinal patient record loads in < 500ms (P95) across all 14 clinics. | Automated k6 load test simulating 300 simultaneous doctor charts. | Redis caching of demographic records; Aurora indexing. | Sprint 11
NFR-PERF-02 | Telehealth Video Latency | Glass-to-glass video latency < 250ms with jitter buffer adaptation. | WebRTC quality telemetry metrics analysis. | LiveKit WebRTC selective forwarding unit with Sydney media relay. | Sprint 10
NFR-AVAIL-01 | System Availability | 99.95% clinical system uptime during core clinic operating hours (7:00 AM - 10:00 PM). | Datadog health check probes with automated alert escalation. | Multi-AZ Aurora, EKS pod autoscaling, multi-node fallback. | Production Go-Live
NFR-SEC-01 | Medical Record Privacy | Zero plain-text storage of clinical notes; AES-256 field-level encryption for sensitive diagnoses. | External cybersecurity penetration test and HIPAA audit. | AWS KMS managed encryption and strict DB column security. | Sprint 10
NFR-SEC-02 | Audit Trail Immutability | Cryptographically verifiable audit log recording doctor ID, timestamp, and patient chart accessed. | Compliance audit inspection by medical legal advisor. | Immutable PostgreSQL write-only audit table with S3 Glacier lock. | Sprint 9

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (24 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Clinical Architecture & FHIR Modeling | Week 1 | 3 Weeks | Clinical workflow discovery, FHIR schema design, doctor UI/UX prototyping, AWS health cloud setup. | Clinical Architecture Document, Figma EHR Prototypes | Milestone 1 Sign-off
Phase 2 | Core EHR, Patient Scheduler & SMS Reminder Engine | Week 4 | 8 Weeks | Develop longitudinal patient record, multi-clinic doctor schedule, two-way SMS reminder microservice. | EHR Core Services in Staging, Scheduler Demo | Milestone 2 Sign-off
Phase 3 | Telehealth Suite, eRx Scripts & Medicare Claiming | Week 12 | 7 Weeks | Develop WebRTC video consultation, Australian eRx integration, Medicare online billing, patient mobile app. | Telehealth Working Demo, Patient Mobile App, eRx Suite | Milestone 3 Sign-off
Phase 4 | Clinical Testing, Security Pentest & Clinic Pilot | Week 19 | 3 Weeks | End-to-end clinical workflow testing, CREST cybersecurity penetration testing, Pilot launch at 2 clinics. | Clinical Audit Sign-off, Pentest Clearance Report | Milestone 4 Sign-off
Phase 5 | Full Network Rollout, Staff Training & Hypercare | Week 22 | 3 Weeks | Phased rollout to remaining 12 clinics, on-site doctor/nurse training, 24/7 dedicated hypercare. | Production Handover Runbook, Final Acceptance Certificate | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & Clinical UX Design | 44 | 638.64 | 28100 | Health SA (12d), PM (8d), Tech Lead (10d), UI/UX (14d) | Fixed Milestone
WBS-02 | Phase 2: Core EHR, Patient Scheduler & SMS Engine | 136 | 523.53 | 71200 | Backend (60d), Tech Lead (26d), PM (20d), QA (20d), DevOps (10d) | Fixed Milestone
WBS-03 | Phase 3: Telehealth, eRx, Medicare & Patient App | 112 | 503.57 | 56400 | Frontend (35d), Mobile (35d), Backend (22d), QA (20d) | Fixed Milestone
WBS-04 | Phase 4: Clinical Testing, Security Pentest & Pilot | 48 | 500 | 24000 | QA Lead (22d), Security SA (8d), PM (10d), DevOps (8d) | Fixed Milestone
WBS-05 | Phase 5: Full Rollout, Clinical Training & Hypercare | 35 | 472.86 | 16550 | Tech Lead (11d), PM (12d), Frontend (6d), Backend (6d) | Fixed Milestone
Subtotal Professional Services (375 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Clinical Architecture Sign-off | 20% | 43175 | Nov 16, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | EHR Record Engine & Scheduler Staging Demo | 25% | 53968.75 | Jan 11, 2027 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Telehealth & eRx Feature Complete Release | 30% | 64762.5 | Mar 01, 2027 (End Sprint 8) | Due within 14 days of gate approval
Milestone 4 | Security Pentest Sign-off & 2-Clinic Pilot Go-Live | 15% | 32381.25 | Apr 05, 2027 (End Sprint 10) | Due within 14 days of gate approval
Milestone 5 | Full Network Rollout & 90-Day Hypercare Sign-off | 10% | 21587.5 | Apr 26, 2027 (Final Gate) | Due within 30 days of sign-off