## Overview
PROPOSAL: CLOUD HOTEL PMS & GUEST EXPERIENCE SUITE
Client: Coastal Stay Hotels Pty Ltd ¦ Proposal ID: PRP-2026-PMS-04 ¦ Date: 20 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | Coastal Stay Hotels Pty Ltd | Presale Solution Lead | Oliver Vance (Principal Hospitality Architect)
Project Code | PBL6-COAST-PMS-2026 | Delivery Manager | Clare Montgomery (Senior Hospitality Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 09 November 2026
Primary Objective | Deploy Unified Cloud PMS across 3 Properties (220 Rooms), Channel Manager & Salto Key Sync | Total Delivery Duration | 26 Calendar Weeks (3 Rollout Waves)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | Coastal Stay operates legacy on-premise PMS servers from 2013 with impending vendor end-of-life. Manual channel updates cause costly double-bookings, paper housekeeping delays check-ins, and server failures create severe operational downtime.
Proposed Strategic Solution | We propose deploying 'CoastCloud PMS': A modern cloud SaaS hospitality platform integrating multi-property reservations, automated two-way OTA channel distribution, mobile housekeeping status, Salto digital key encoding, and automated Xero journal sync.
Measurable Business Impact | • 100% elimination of double-bookings via sub-second two-way OTA channel synchronization. • 2 hours/day saved per property in manual rate uploading across Booking.com and Expedia. • Room turnover inspection time reduced by 35% through mobile housekeeping tasking. • Zero on-premise server maintenance overhead via AWS Australia multi-tenant cloud hosting.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $166,400 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $16,640 | Payment Term Milestone Structure | 5 Deliverable-Based Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $183,040 ex GST | Ongoing SaaS Subscription | AUD $4,100/month (220 rooms @ $18.60/room/mo)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
Hospitality Solution Architect | Vendor | Part-Time (30%) | Hotel system architecture, OTA channel manager protocols, Salto lock integration | PMS Architecture Blueprint, Integration Specifications | Principal
Project Manager | Vendor | Full-Time (100%) | Rollout wave management across Byron Bay, Gold Coast, Sydney; vendor governance | Project Plan, Wave Go-Live Checklist, Status Reports | Senior
Technical Lead | Vendor | Full-Time (100%) | Core PMS engine, database schema, POS and Xero interface connectors, CI/CD pipeline | PMS Core Architecture, Data Migration Scripts | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Reservation state machine, channel manager webhooks, billing folios, night audit engine | REST APIs, Night Audit Workers, Xero Connector | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | Front desk web dashboard, visual tape chart (room grid), direct website booking engine | Front Desk Web Application, Direct Booking Widget | Senior
Mobile Web Specialist | Vendor | Part-Time (50%) | Responsive mobile housekeeping app, maintenance ticketing interface | Mobile Housekeeping PWA | Senior
QA / Hospitality Test Lead | Vendor | Full-Time (100%) | Folio balance testing, channel sync validation, night audit reconciliation, UAT | Test Plans, Folio Financial Audit Report | Senior
UI/UX Product Designer | Vendor | Phase 1 & 2 (50%) | Tape chart ergonomics, quick check-in workflow, mobile housekeeping UI | Figma Design System, Interactive Prototypes | Senior
Product Owner (PO) | Client | Key Stakeholder (40%) | Room setup design, rate plan hierarchy sign-off, UAT lead | Rate Matrix, UAT Acceptance Certificates | Executive
Group Financial Controller | Client | Key Stakeholder (20%) | Xero chart of accounts, GST tax rule validation, payment gateway sign-off | Financial Sign-off, Accounting Mapping | Executive

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Migration of historical guest reservation data from legacy 2013 on-premise database. | High | Medium | Run test extraction scripts in Byron Bay during Discovery; sanitize data into standard CSV. | Tech Lead
RSK-02 | Risk | Property internet drop during front desk check-in peak at coastal hotels. | Medium | Medium | Enable local PWA offline buffering for key check-in details with automatic background sync. | Frontend Lead
ASM-01 | Assumption | Client property staff available for scheduled training workshops prior to each wave go-live. | High | N/A | Training scheduled in 2-hour shifts to prevent hotel operational disruption. | Client PM
DEP-01 | Dependency | Salto door lock server IP access and API license confirmed by Salto technician. | High | Open | Client confirmed Salto local server access ready for test encoder in Sprint 3. | Client IT

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-PMS-01 | Core Front Desk | Interactive Visual Tape Chart | Front desk staff shall view, drag-and-drop, and assign 220 rooms on an interactive daily/monthly tape chart. | Must-Have | High | Sprint 1
FR-PMS-02 | Core Front Desk | Guest Folio & Split Billing | System shall manage guest charges, room splits, restaurant debits, and generate compliant GST tax invoices. | Must-Have | High | Sprint 2
FR-CHN-01 | Channel Manager | Two-Way OTA Synchronization | System shall push room rates/availability and pull bookings from Booking.com, Expedia, and Airbnb in <30s. | Must-Have | High | Sprint 3
FR-HK-01 | Housekeeping | Mobile Room Status Updating | Attendants shall view assigned room list on mobile and mark rooms Clean, Inspected, or Maintenance. | Must-Have | Medium | Sprint 4
FR-INT-01 | Integrations | Salto Key Card Encoder API | Front desk check-in shall trigger RFID keycard creation directly via local Salto encoder integration. | Must-Have | High | Sprint 5
FR-INT-02 | Integrations | Lightspeed Restaurant POS Interface | Gold Coast restaurant staff shall charge food & beverage bills directly to guest room folios via room/name lookup. | Must-Have | Medium | Sprint 5
FR-INT-03 | Integrations | Automated Xero Journal Sync | Night audit shall automatically generate and export balanced daily revenue and payment journals to Xero. | Must-Have | Medium | Sprint 6
FR-BKG-01 | Direct Booking | Website Direct Booking Engine | Responsive website booking engine with live calendar, room photos, add-on packages, and Stripe payment. | Must-Have | Medium | Sprint 6
FR-RPT-01 | Reporting | Group Executive Dashboard | Head office shall view consolidated group RevPAR, ADR, occupancy rates, and forward booking pace. | Must-Have | Medium | Sprint 7

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Front Desk Web App | Next.js 15 (React 19, TypeScript) | 15.0+ | Fast interactive tape chart rendering, responsive UI, zero-install browser deployment. | Open Source / AWS | Multi-AZ CloudFront
Mobile Housekeeping | Progressive Web App (PWA) | N/A | Offline-capable lightweight web app running on any iOS/Android smartphone or tablet. | Open Source / Web | Cached Service Worker
Core Backend Services | NestJS (Node.js Enterprise) | 10.4+ | Modular TypeScript microservices for reservations, rate engine, and channel connectors. | Open Source / AWS EKS | Auto-scaling Pods (2-8)
Hospitality Database | PostgreSQL (AWS Aurora) | 16.x | Strict transactional consistency for financial folios, multi-tenant property data isolation. | AWS Managed Aurora | Multi-AZ Auto-Failover
Cache & Lock Service | Redis Enterprise | 7.2+ | Sub-millisecond room inventory reservation locks during simultaneous online bookings. | AWS ElastiCache | Multi-AZ Replication
Cloud Infrastructure | AWS Sydney (ap-southeast-2) | N/A | Australian data residency compliance; low latency (< 20ms) across NSW and QLD hotels. | AWS Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Channel Sync Latency | OTA rate and availability changes synchronized to Booking.com/Expedia in < 30 seconds. | Automated synthetic channel webhook response monitoring. | Asynchronous message queue decoupling with Redis buffer. | Sprint 8
NFR-PERF-02 | Check-in Transaction Time | Front desk check-in and room key generation completed in < 15 seconds. | Usability time-and-motion testing during staff training. | Optimized single-screen check-in workflow with pre-cached folios. | Sprint 7
NFR-AVAIL-01 | System Availability | 99.95% system uptime (< 21.6 minutes unscheduled downtime/month). | Continuous external health monitoring from Sydney & Brisbane. | AWS Multi-AZ Aurora and redundant application containers. | Production Go-Live
NFR-SEC-01 | Payment Data Security | PCI-DSS Level 1 compliance; credit cards tokenized via Stripe/Tyro with zero raw PAN stored. | Third-party PCI compliance attestation. | Client-side payment tokenization and encrypted card tokens. | Sprint 7

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (26 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Discovery, Room Matrix & Architecture Setup | Week 1 | 3 Weeks | Property room inventory audit, rate plan mapping, Salto & POS technical discovery, AWS setup. | Architecture Blueprint, Rate Configuration Matrix | Milestone 1 Sign-off
Phase 2 | Core PMS Engine, Channel Manager & Xero Sync | Week 4 | 8 Weeks | Develop visual tape chart, reservation state machine, two-way OTA channel sync, Xero journals. | PMS Core Staging Release, Channel Sync Demo | Milestone 2 Sign-off
Phase 3 | Integrations (Salto, POS) & Wave 1 Byron Bay Pilot | Week 12 | 6 Weeks | Salto key encoder integration, Lightspeed POS interface, Wave 1 Byron Bay go-live and training. | Byron Bay Pilot Go-Live Certificate, Salto Connector | Milestone 3 Sign-off
Phase 4 | Wave 2 (Gold Coast) & Wave 3 (Sydney CBD) Rollout | Week 18 | 5 Weeks | Data migration and go-live for Gold Coast (restaurant POS active) and Sydney CBD properties. | Wave 2 & Wave 3 Go-Live Acceptance Certificates | Milestone 4 Sign-off
Phase 5 | Group Dashboard Handover & 90-Day Hypercare | Week 23 | 4 Weeks | Executive reporting dashboard sign-off, final staff training, 24/7 on-call operational hypercare. | Final Handover Sign-off, Hypercare Acceptance | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Discovery, Architecture & Configuration | 38 | 634.21 | 24100 | Hospitality SA (10d), PM (8d), Tech Lead (10d), UI/UX (10d) | Fixed Milestone
WBS-02 | Phase 2: Core PMS, Tape Chart & Channel Sync | 120 | 520 | 62400 | Backend (55d), Frontend (30d), Tech Lead (15d), QA (20d) | Fixed Milestone
WBS-03 | Phase 3: Integrations (Salto, POS) & Wave 1 Pilot | 90 | 510 | 45900 | Backend (30d), Frontend (25d), QA (20d), PM (15d) | Fixed Milestone
WBS-04 | Phase 4: Wave 2 (Gold Coast) & Wave 3 (Sydney) Rollout | 45 | 480 | 21600 | PM (15d), Tech Lead (10d), Backend (10d), QA (10d) | Fixed Milestone
WBS-05 | Phase 5: Executive Reporting & Hypercare Support | 27 | 459.26 | 12400 | PM (10d), Tech Lead (7d), Backend (5d), Frontend (5d) | Fixed Milestone
Subtotal Professional Services (320 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Discovery Architecture Sign-off | 20% | 36608 | Nov 09, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Core PMS & Channel Manager Staging Verification | 25% | 45760 | Jan 04, 2027 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Wave 1 Byron Bay Pilot Go-Live & Salto Key Sign-off | 30% | 54912 | Feb 15, 2027 (Wave 1 Go-Live) | Due within 14 days of gate approval
Milestone 4 | Wave 2 (Gold Coast) & Wave 3 (Sydney) Go-Live | 15% | 27456 | Mar 22, 2027 (Wave 3 Go-Live) | Due within 14 days of gate approval
Milestone 5 | Final Handover & 90-Day Hypercare Sign-off | 10% | 18304 | Apr 19, 2027 (Final Gate) | Due within 30 days of sign-off