## Overview
PROPOSAL: ENTERPRISE FLEET TELEMATICS & DYNAMIC TMS PLATFORM
Client: TransOcean Freight & Logistics Ltd ¦ Proposal ID: PRP-2026-TRN-05 ¦ Date: 24 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | TransOcean Freight & Logistics Ltd | Presale Solution Lead | Garrett Stone (Principal Supply Chain Architect)
Project Code | PBL6-TRN-TMS-2026 | Delivery Manager | Nathaniel Cross (Senior Logistics Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 16 November 2026
Primary Objective | Deploy Live Geotab Telematics Hub, AI Backhaul Optimizer & Driver Mobile App across 350 Trucks | Total Delivery Duration | 22 Calendar Weeks (11 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | TransOcean suffers from 28% deadhead empty miles ($1.8M fuel loss), 5-day DSO invoice latency from paper bills of lading, compliance risks from manual fatigue tracking, and high customer tracking call overhead.
Proposed Strategic Solution | We propose 'FleetSync Cloud TMS': An event-driven freight platform featuring sub-5-second Geotab telematics streaming, AI-powered backhaul load matching, native driver mobile app with offline OCR POD scanning, and automated SAP invoicing.
Measurable Business Impact | • Deadhead empty miles reduced from 28% down to under 12%, saving an estimated $1.1M in annual fuel. • Order-to-cash DSO accelerated from 5 business days down to < 2 minutes via automated mobile POD. • Customer status inquiry phone calls reduced by 85% via automated EDI 214 and tracking portal. • 100% compliance with NHVR driver fatigue regulations through automated EWD telematics sync.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $182,500 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $18,250 | Payment Term Milestone Structure | 5 Deliverable-Based Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $200,750 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,600/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
Supply Chain Solution Architect | Vendor | Part-Time (35%) | Event streaming architecture, Geotab telemetry pipeline, SAP IDoc connector design | TMS Architecture Blueprint, Telemetry Interface Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint orchestration, depot rollout coordination, driver change management planning | Project Burndown, Depot Rollout Plan, Status Reports | Senior
Technical Lead | Vendor | Full-Time (100%) | Kafka streaming engine, route optimization algorithms, driver app offline sync | Core Architecture, CI/CD, Routing Microservice | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Geotab streaming ingest, backhaul load matching engine, SAP billing connector, EDI 204/214 | REST/gRPC APIs, Kafka Ingestion Workers, SAP Connector | Senior
Senior Mobile Engineers (2) | Vendor | Full-Time (200%) | Flutter cross-platform driver app, camera OCR POD scanning, offline SQLite cache | Driver Android & iOS Apps, Offline Sync Engine | Senior
QA / Logistics Test Lead | Vendor | Full-Time (100%) | Route algorithm validation, offline sync stress testing, SAP end-to-end invoice audits | Automated Test Suite, Field Pilot Test Report | Senior
UI/UX Product Designer | Vendor | Phase 1 & 2 (50%) | Dispatcher multi-monitor map UI, rugged high-contrast driver mobile ergonomics | Figma Design System, Interactive Prototypes | Senior
DevOps & Cloud Engineer | Vendor | Part-Time (40%) | AWS Kafka (MSK), EKS auto-scaling, Prometheus telemetry monitoring | Terraform Scripts, Telematics Cloud Infrastructure | Senior
Product Owner (PO) | Client | Key Stakeholder (40%) | Dispatch rule specification, carrier SLA criteria, pilot fleet oversight | TMS Rulebook, Pilot Acceptance Sign-off | Executive
Enterprise SAP IT Lead | Client | Key Partner (25%) | SAP IDoc / RFC interfaces, firewall setup, sandbox credentials | SAP Interface Configurations, Credentials | Lead

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Driver cellular dead zones across regional outback routes causing app data stalls. | High | High | Enforce robust local SQLite offline storage with automated background queue sync upon signal restore. | Mobile Lead
RSK-02 | Risk | High telemetry ingestion volume (350 trucks streaming every 5s = 70 events/sec) overwhelming DB. | Medium | Medium | Deploy Kafka stream buffering and timescale time-series database partitioning. | Tech Lead
ASM-01 | Assumption | Geotab telematics hardware installed and firmware updated across all 350 trucks. | High | N/A | Client fleet team confirmed Geotab hardware installed across 100% of fleet. | Client PM
DEP-01 | Dependency | SAP S/4HANA IDoc / RFC sandbox connection provisioned by Sprint 2. | High | Open | Client SAP team scheduled connector provisioning for Nov 24. | Client IT

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-TEL-01 | Telematics Hub | Live Geotab GPS Streaming | System shall ingest vehicle GPS, speed, and odometer every 5s via Kafka and update live dispatcher map. | Must-Have | High | Sprint 1
FR-TEL-02 | Telematics Hub | Automated Geofence Triggers | System shall detect vehicle arrival and departure at depots/customer sites, auto-updating trip status. | Must-Have | Medium | Sprint 2
FR-OPT-01 | Route Optimizer | AI Backhaul Load Matching | System shall analyze empty return corridors and recommend high-margin spot freight loads. | Must-Have | High | Sprint 3
FR-OPT-02 | Route Optimizer | Commercial Truck Turn-by-Turn | System shall calculate truck routes accounting for B-double bridge weight, tunnel hazmat, and height limits. | Must-Have | High | Sprint 4
FR-MOB-01 | Driver Mobile App | Camera OCR Proof-of-Delivery (POD) | Driver shall take photo of signed paper manifest; system extracts consignment ID and signature via OCR. | Must-Have | High | Sprint 5
FR-MOB-02 | Driver Mobile App | Offline Queue Synchronization | Driver app shall store all trip logs, checklist forms, and POD scans in offline SQLite during dead zones. | Must-Have | High | Sprint 5
FR-SAP-01 | ERP Integration | Instant SAP Billing Dispatch | Upon verified POD upload, system shall trigger SAP billing IDoc in <2 minutes, auto-generating invoice. | Must-Have | High | Sprint 6
FR-EDI-01 | Customer EDI | Automated EDI 214 Milestone Dispatch | System shall transmit EDI 214 shipment tracking updates to enterprise shipper systems at every key milestone. | Must-Have | Medium | Sprint 7
FR-FAT-01 | Safety & Compliance | NHVR Driver Fatigue Counter | System shall monitor driver rest breaks and trigger audible alerts when driver approaches 12-hour limit. | Must-Have | Medium | Sprint 8

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Dispatcher Web Portal | Next.js 15 (React 19, TypeScript) | 15.0+ | Multi-monitor map rendering using Mapbox GL, real-time WebSockets vehicle telemetry. | Open Source / AWS | Multi-AZ CloudFront
Driver Mobile App | Flutter 3.x (Dart) | 3.24+ | Single cross-platform app with ML Kit Camera OCR, local SQLite caching, offline sync engine. | Open Source / Native | Local Encrypted SQLite
Event Ingestion Engine | Apache Kafka (AWS MSK) | 3.7+ | High-throughput event streaming ingesting 70+ telematics events/sec with zero packet loss. | AWS Managed Kafka | 3-AZ Cluster
Core Backend Services | Go (Golang) & NestJS | 1.23+ / 10+ | Go for high-speed telematics processing; NestJS for dispatch business logic and SAP connectors. | Open Source / AWS EKS | Auto-scaling Pods (3-12)
Time-Series & Primary DB | PostgreSQL Aurora & TimescaleDB | 16.x | PostgreSQL for orders and dispatch; TimescaleDB hypertable partitioning for GPS telemetry logs. | AWS Aurora / Timescale | Multi-AZ Auto-Failover
Cloud Infrastructure | AWS Sydney (ap-southeast-2) | N/A | Low-latency AWS Australia region, VPC peering, KMS encryption. | AWS Cloud Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | GPS Ingestion Latency | Telematics data point ingested, geofence verified, and rendered on dispatcher map in < 1.5s. | k6 automated streaming load benchmark simulating 500 trucks. | Kafka distributed topic partitioning and WebSockets. | Sprint 9
NFR-PERF-02 | Mobile POD Upload Speed | Compressed POD image and OCR metadata synchronized within 3 seconds of cellular reconnect. | Network throttling simulation drill (2G/3G network conditions). | Client-side image compression (WEBP) before queue transmission. | Sprint 8
NFR-AVAIL-01 | System Availability | 99.95% system uptime (< 21.6 minutes unscheduled downtime/month). | Continuous synthetic health monitoring of Kafka brokers and APIs. | Multi-AZ EKS cluster, multi-broker Kafka, Aurora failover. | Production Go-Live
NFR-SEC-01 | Data Security | AES-256 encryption at rest; TLS 1.3 in transit; driver location data restricted via strict RBAC. | Cybersecurity audit scan and penetration test. | AWS KMS managed customer master keys and IAM roles. | Sprint 10

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (22 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Telematics Architecture & Dispatch UX | Week 1 | 3 Weeks | Geotab API data stream discovery, SAP IDoc mapping, dispatcher Mapbox prototype, AWS setup. | Architecture Blueprint, Interactive Figma Prototypes | Milestone 1 Sign-off
Phase 2 | Telematics Streaming Hub & Dispatch Engine | Week 4 | 7 Weeks | Develop Kafka telemetry ingest, live map wallboard, geofence engine, backhaul load matcher. | Telematics Hub in Staging, Geofence Demo | Milestone 2 Sign-off
Phase 3 | Driver Mobile App, OCR POD & SAP Connector | Week 11 | 6 Weeks | Develop Flutter driver app, offline SQLite sync, camera OCR POD capture, SAP billing connector. | Driver App Builds, Automated SAP Invoicing Demo | Milestone 3 Sign-off
Phase 4 | Pilot Corridor Launch (50 Trucks) & Pentest | Week 17 | 3 Weeks | Deploy to 50 pilot trucks in Sydney-Melbourne corridor, field testing, security pentest. | Pilot Corridor Acceptance Certificate, Pentest Report | Milestone 4 Sign-off
Phase 5 | Full Fleet Rollout (350 Trucks) & 90-Day Hypercare | Week 20 | 3 Weeks | Depot rollout across Brisbane, Melbourne, Adelaide, Perth, driver training, 24/7 hypercare. | Full Fleet Acceptance Certificate, Final Handover | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & UI Design | 40 | 645 | 25800 | Supply Chain SA (12d), PM (8d), Tech Lead (10d), UI/UX (10d) | Fixed Milestone
WBS-02 | Phase 2: Telematics Streaming Hub & Backhaul Engine | 125 | 526.4 | 65800 | Backend (55d), Tech Lead (25d), PM (15d), QA (20d), DevOps (10d) | Fixed Milestone
WBS-03 | Phase 3: Driver Mobile App, OCR POD & SAP Connector | 105 | 508.57 | 53400 | Mobile (45d), Backend (25d), QA (20d), PM (15d) | Fixed Milestone
WBS-04 | Phase 4: 50-Truck Pilot, Security Pentest & UAT | 48 | 487.5 | 23400 | QA Lead (20d), SA (8d), PM (10d), DevOps (10d) | Fixed Milestone
WBS-05 | Phase 5: Fleet Rollout, Driver Training & Hypercare | 32 | 440.63 | 14100 | Tech Lead (10d), PM (10d), Mobile (6d), Backend (6d) | Fixed Milestone
Subtotal Professional Services (350 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 40150 | Nov 16, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Telematics Hub & Live Map Staging Verification | 25% | 50187.5 | Jan 04, 2027 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Driver App & Automated SAP Invoicing Demo | 30% | 60225 | Feb 15, 2027 (End Sprint 7) | Due within 14 days of gate approval
Milestone 4 | 50-Truck Pilot Go-Live & Security Clearance | 15% | 30112.5 | Mar 22, 2027 (End Sprint 9) | Due within 14 days of gate approval
Milestone 5 | Full Fleet Rollout & 90-Day Hypercare Sign-off | 10% | 20075 | Apr 12, 2027 (Final Gate) | Due within 30 days of sign-off