## Overview
PROPOSAL: NEXT-GEN INTERACTIVE LMS & AI PROCTORING PLATFORM
Client: EduVantage Global Academy Ltd ¦ Proposal ID: PRP-2026-EDV-06 ¦ Date: 18 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | EduVantage Global Academy Ltd | Presale Solution Lead | Dr. Kevin Liang (Principal EdTech Architect)
Project Code | PBL6-EDV-LMS-2026 | Delivery Manager | Sarah Jenkins (Senior Agile Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 16 November 2026
Primary Objective | Deliver Scalable Cloud LMS, Mobile Apps, and AI-Powered Remote Proctoring Engine | Total Delivery Duration | 20 Calendar Weeks (10 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | EduVantage faces high invigilation costs ($180k/semester) and exam integrity risks. Legacy LMS cannot handle concurrent examination loads of 15,000 students.
Proposed Strategic Solution | We propose 'EduVantage Cloud LMS & ProctorAI': AWS EKS auto-scaling learning portal with WebRTC live classrooms, on-device AI proctoring analyzing webcam and audio feeds, and automated Turnitin similarity scoring.
Measurable Business Impact | • Invigilation operational expenditure reduced by 75% via automated AI screening. • Zero server downtime during 25,000 concurrent student final exams. • Exam grading turnaround accelerated from 3 weeks to 48 hours. • Student mobile satisfaction score increased to > 4.8/5.0.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $168,000 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $16,800 | Payment Term Milestone Structure | 5 Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $184,800 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,500/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
EdTech Solution Architect | Vendor | Part-Time (40%) | Cloud video architecture, AI proctoring model pipeline, FERPA/GDPR compliance | Architecture Blueprint, Security Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint governance, stakeholder demos, budget and delivery schedule | Project Plan, Risk Register | Senior
Technical Lead | Vendor | Full-Time (100%) | Full-stack architecture, WebRTC video scaling, code review governance | Core Codebase, CI/CD Pipeline | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Course management APIs, assessment engine, gradebook microservice | REST/GraphQL APIs, Data Models | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | Next.js student/teacher web portals, interactive grading studio | Web Portals, UI Components | Senior
Senior Mobile Engineer | Vendor | Full-Time (100%) | React Native student mobile app with offline video caching | iOS and Android Mobile Apps | Senior
QA / Test Automation Lead | Vendor | Full-Time (100%) | Load testing concurrent exam submissions, proctoring accuracy test | Test Automation Suites | Senior

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Webcam AI false positives during exam proctoring (poor lighting, ambient noise). | High | Medium | Configure confidence score thresholds; flag for human secondary review rather than immediate auto-fail. | AI Lead
RSK-02 | Risk | Browser extension bypasses or dual-monitor cheating during unproctored quizzes. | Medium | Medium | Deploy secure lockdown browser SDK with full screen capture and clipboard restrictions. | Security Lead
DEP-01 | Dependency | Zoom SDK and Turnitin API enterprise licensing credentials provisioned by Week 2. | High | Open | Client procurement finalizing contract with Turnitin / Zoom. | Client PM

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-LMS-01 | Course Engine | Interactive Video Lessons | System shall stream adaptive bitrate video with interactive timestamped quizzes and student notes. | Must-Have | Medium | Sprint 1
FR-LMS-02 | Course Engine | Offline Mobile Downloads | Mobile app shall securely download encrypted video lessons for offline study with automated license expiry. | Must-Have | High | Sprint 3
FR-PRC-01 | AI Proctoring | Face & Gaze Tracking | System shall detect multiple faces, continuous gaze divergence, and absent test-taker via client-side WebAssembly AI. | Must-Have | High | Sprint 4
FR-PRC-02 | AI Proctoring | Acoustic Anomaly Flagging | System shall analyze ambient microphone audio for whispered speech or secondary device audio during exams. | Must-Have | High | Sprint 5
FR-EXM-01 | Assessment Studio | Automated Exam Grading | System shall auto-grade multiple choice, code executions, and forward essay questions to rubric grading dashboard. | Must-Have | Medium | Sprint 6
FR-SEC-01 | Integrity & Compliance | Turnitin Plagiarism Sync | System shall automatically submit written assignments to Turnitin API and display similarity index report. | Must-Have | Medium | Sprint 7

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Web Learning Portal | Next.js 15 (React 19, TypeScript) | 15.0+ | Server-side rendering, accessible WCAG 2.1 AA UI components, Tailwind CSS. | Open Source / AWS | Global CloudFront CDN
Student Mobile App | React Native (Expo SDK 52) | 0.76+ | Cross-platform iOS and Android with background download manager and SQLite storage. | Open Source | Encrypted Offline Storage
Core LMS Microservices | Node.js (NestJS) & Go | 20.x / 1.23 | Modular enterprise microservices with high concurrent exam submission throughput. | Open Source / AWS EKS | Auto-scaling Pods (3-20)
AI Proctoring Engine | ONNX Runtime & WebAssembly | 1.19+ | Client-side edge inference for zero-latency facial landmark and gaze detection. | Open Source Edge AI | Zero server video storage
Relational Database | PostgreSQL (AWS Aurora) | 16.x | ACID transactional compliance for student enrollments and gradebook records. | AWS Aurora Multi-AZ | Automated Read Replicas

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Concurrent Exam Concurrency | Support 20,000 concurrent exam takers submitting responses with P95 latency < 300ms. | k6 load test simulating national finals week. | Redis cluster caching and async queue worker pods. | Sprint 9
NFR-AVAIL-01 | High Availability | 99.95% system uptime availability during semester exam periods. | Datadog synthetic probes with auto-healing pods. | Multi-AZ AWS deployment with auto-failover. | Production Go-Live
NFR-SEC-01 | Student Privacy (FERPA) | All student telemetry and proctoring metadata encrypted with AES-256; video destroyed post-audit. | External FERPA and GDPR audit clearance. | AWS KMS Customer Managed Keys. | Sprint 8

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (20 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & UX Design | Week 1 | 3 Weeks | Requirements finalization, Figma UI design system, proctoring algorithm proof of concept. | Architecture Blueprint, Interactive Figma Prototype | Milestone 1 Sign-off
Phase 2 | Core LMS Portal & Course Delivery Engine | Week 4 | 6 Weeks | Develop course player, enrollment workflows, assignment submissions, video transcoding. | LMS Portal in Staging, Video Player Demo | Milestone 2 Sign-off
Phase 3 | AI Proctoring Engine & Mobile Learning App | Week 10 | 6 Weeks | Develop client-side proctoring engine, lockdown exam browser, React Native mobile apps. | Proctoring Test Suite, TestFlight Mobile Build | Milestone 3 Sign-off
Phase 4 | Load Testing, Security Pentest & Pilot Trial | Week 16 | 3 Weeks | 20,000 concurrent user load test, security penetration test, trial exams with 500 students. | Load Test Report, Security Clearance, UAT Sign-off | Milestone 4 Sign-off
Phase 5 | Production Deployment, Rollout & Hypercare | Week 19 | 2 Weeks | AWS EKS production launch, data migration, 24/7 exam monitoring hypercare. | Production Handover Runbook, Final Acceptance | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & UI/UX Design | 36 | 625 | 22500 | Solution Architect (10d), PM (8d), Tech Lead (8d), UI/UX (10d) | Fixed Milestone
WBS-02 | Phase 2: Core LMS Portal & Assessment Engine | 120 | 525 | 63000 | Backend (50d), Frontend (35d), Tech Lead (15d), QA (20d) | Fixed Milestone
WBS-03 | Phase 3: AI Proctoring Engine & Mobile Learning Apps | 100 | 530 | 53000 | AI/Mobile (45d), Backend (25d), QA (20d), PM (10d) | Fixed Milestone
WBS-04 | Phase 4: Load Testing, Security Pentest & UAT | 40 | 487.5 | 19500 | QA Lead (20d), PM (8d), SA (4d), DevOps (8d) | Fixed Milestone
WBS-05 | Phase 5: Production Deployment & Hypercare | 24 | 416.67 | 10000 | Tech Lead (8d), PM (8d), DevOps (4d), Mobile (4d) | Fixed Milestone
Subtotal Professional Services (320 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 36960 | Nov 16, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Core LMS Staging Demo & Video Player Gate | 25% | 46200 | Dec 28, 2026 (End Sprint 3) | Due within 14 days of gate approval
Milestone 3 | AI Proctoring & Mobile App Feature Complete | 30% | 55440 | Feb 08, 2027 (End Sprint 6) | Due within 14 days of gate approval
Milestone 4 | Load Test Clearance & 500-Student Pilot Gate | 15% | 27720 | Mar 01, 2027 (End Sprint 8) | Due within 14 days of gate approval
Milestone 5 | Production Go-Live & Semester Final Acceptance | 10% | 18480 | Mar 22, 2027 (Final Gate) | Due within 30 days of sign-off