## Overview
PROPOSAL: SMART COMMERCIAL BUILDING & TENANT EXPERIENCE PLATFORM
Client: Horizon Towers Asset Management Ltd ¦ Proposal ID: PRP-2026-HRZ-07 ¦ Date: 21 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | Horizon Towers Asset Management Ltd | Presale Solution Lead | Harrison Ford (Principal PropTech Architect)
Project Code | PBL6-HRZ-PROP-2026 | Delivery Manager | Emily Watson (Senior PropTech Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 23 November 2026
Primary Objective | Deploy Mobile Tenant App with NFC Access, Smart BMS Control & Visitor Management | Total Delivery Duration | 18 Calendar Weeks (9 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | Horizon Towers experiences lobby turnstile congestion and $45k annual keycard replacement overhead. Disconnected facility management delays repairs and wastes energy in empty hybrid office zones.
Proposed Strategic Solution | We propose 'HorizonConnect': An enterprise PropTech suite comprising native iOS/Android apps with Apple/Google Wallet NFC access, automated visitor QR passes, BMS IoT climate adjustment, and facility work order ticketing.
Measurable Business Impact | • 100% elimination of physical plastic badge issuance for new tenant onboarding. • Lobby morning check-in throughput accelerated from 12 guests/min to 45 guests/min. • Common zone HVAC energy consumption reduced by 18% via occupancy sensor rules. • Tenant maintenance ticket resolution cycle reduced from 4.2 days to < 6 hours.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $152,000 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $15,200 | Payment Term Milestone Structure | 5 Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $167,200 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,200/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
PropTech Solution Architect | Vendor | Part-Time (40%) | BMS BACnet/Modbus integration, HID Origo access credential architecture | Architecture Blueprint, IoT Interface Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint management, hardware vendor coordination, tenant pilot governance | Project Plan, Risk Register | Senior
Technical Lead | Vendor | Full-Time (100%) | Mobile NFC integration, IoT gateway services, cloud backend governance | Core Codebase, CI/CD Pipeline | Lead
Senior Mobile Engineers (2) | Vendor | Full-Time (200%) | Flutter mobile app, Apple Wallet / Google Wallet NFC integration | iOS and Android Mobile Builds | Senior
Senior Backend Engineer | Vendor | Full-Time (100%) | Facility ticketing engine, visitor QR microservice, BMS polling worker | REST APIs, Database Schemas | Senior
QA / Field Test Lead | Vendor | Full-Time (100%) | Turnstile hardware testing, Bluetooth RSSI calibration, load testing | Test Suite, Hardware Acceptance Report | Senior

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Building turnstile hardware latency exceeding 800ms when reading phone NFC. | High | Low | Use HID Origo native BLE/NFC SDK with local credential caching on mobile device. | Tech Lead
RSK-02 | Risk | Older BMS controllers (BACnet MS/TP) lacking REST API connectivity. | Medium | Medium | Deploy edge IoT gateway bridges converting BACnet to MQTT/HTTPS in basement DCs. | IoT Architect
DEP-01 | Dependency | Turnstile hardware controller network access and IP configuration by building IT. | High | Open | Building facilities manager scheduled network survey for Week 2. | Client Facilities

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-ACC-01 | Access Control | Mobile NFC / BLE Turnstile Unlock | Mobile app shall transmit encrypted credential to turnstiles and elevator readers via NFC/BLE within < 400ms. | Must-Have | High | Sprint 2
FR-ACC-02 | Access Control | Apple & Google Wallet Integration | System shall provision digital building keycards directly into Apple Wallet and Google Wallet passes. | Must-Have | High | Sprint 3
FR-VST-01 | Visitor Management | Pre-Registered QR Code Passes | Tenants shall invite visitors via app, generating dynamic 1-time QR codes for contactless lobby kiosk check-in. | Must-Have | Medium | Sprint 4
FR-FAC-01 | Smart Facilities | HVAC & Lighting On-Demand Override | Authorized tenant admins shall request after-hours AC and lighting for specific floor zones with automated billing. | Must-Have | Medium | Sprint 5
FR-RSV-01 | Amenity Booking | Meeting Room & Hot Desk Booking | Tenants shall view live room availability, book spaces, and sync calendar invites with Outlook 365. | Must-Have | Medium | Sprint 6

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Tenant Mobile App | Flutter 3.x (Dart) | 3.24+ | Cross-platform mobile app with Apple Wallet NFC PassKit & Google Wallet API. | Open Source / Native | Redundant App Store CDN
Admin Web Portal | React 19 & Next.js 15 | 15.0+ | Responsive property management web console with live floor plan status. | Open Source / AWS | CloudFront Edge
Core Facility API | NestJS (Node.js) | 10.4+ | Modular TypeScript microservices with WebSockets for real-time ticket alerts. | Open Source / AWS EKS | Auto-scaling Pods (2-10)
IoT BMS Gateway | Go (Golang MQTT Service) | 1.23+ | Lightweight MQTT broker gateway connecting BACnet/Modbus building controllers. | Open Source | Edge Server in Tower Basement
Cloud Database | PostgreSQL (AWS Aurora) | 16.x | ACID transactional database with Row-Level Security for multi-tenant isolation. | AWS Aurora Multi-AZ | Automated Daily Backups

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Turnstile NFC Unlock Time | Mobile badge credential read and barrier unlock trigger completes in < 400ms (P99). | Automated hardware test rig with 1,000 tap cycles. | Local crypto key validation on mobile client. | Sprint 7
NFR-AVAIL-01 | Offline Access Continuity | Turnstiles continue granting access to registered tenant badges if cloud Internet drops. | Simulated Internet sever test at building core switch. | Local hardware reader credential buffer. | Pre-Commissioning
NFR-SEC-01 | Credential Encryption | All digital credentials encrypted using AES-128 GCM; tokenized against replay attacks. | Independent physical and digital security audit. | HID Origo secure enclave tokenization. | Sprint 8

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (18 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & Hardware Survey | Week 1 | 3 Weeks | Site visits across 8 towers, turnstile hardware audit, BMS protocol survey, Figma UI design. | Hardware Audit Report, Architecture Spec, Figma Prototype | Milestone 1 Sign-off
Phase 2 | Core Platform, Visitor Management & BMS API | Week 4 | 6 Weeks | Develop tenant management API, visitor QR engine, BACnet/Modbus IoT gateway connectors. | Staging API, Visitor Kiosk Demo, IoT Gateway Build | Milestone 2 Sign-off
Phase 3 | Mobile Apps & Wallet NFC Credentials | Week 10 | 5 Weeks | Develop Flutter mobile app, Apple Wallet / Google Wallet pass generation, turnstile unlock test. | TestFlight / Play Console Mobile Builds, Turnstile Video Demo | Milestone 3 Sign-off
Phase 4 | Pilot Rollout & Hardware Integration (Tower 1) | Week 15 | 2 Weeks | Live hardware deployment at Horizon Tower Sydney (2,500 occupants), turnstile pilot testing. | Tower 1 Commissioning Acceptance Certificate | Milestone 4 Sign-off
Phase 5 | Full Portfolio Rollout (Towers 2-8) & Hypercare | Week 17 | 2 Weeks | Rollout to remaining 7 commercial towers, property manager training, 60-day hypercare. | Portfolio Acceptance Sign-off, Final Handover | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Site Survey & UI/UX Design | 32 | 640.63 | 20500 | Solution Architect (10d), PM (8d), Tech Lead (6d), UI/UX (8d) | Fixed Milestone
WBS-02 | Phase 2: Core Platform, Visitor Engine & BMS Gateway | 110 | 520 | 57200 | Backend (45d), Tech Lead (25d), IoT Eng (20d), QA (20d) | Fixed Milestone
WBS-03 | Phase 3: Mobile Apps & Apple/Google Wallet NFC | 90 | 533.33 | 48000 | Mobile (45d), Backend (20d), QA (15d), PM (10d) | Fixed Milestone
WBS-04 | Phase 4: Pilot Deployment & Hardware Sign-off (Tower 1) | 36 | 472.22 | 17000 | QA Lead (14d), Tech Lead (10d), PM (8d), DevOps (4d) | Fixed Milestone
WBS-05 | Phase 5: Portfolio Rollout (7 Towers) & Hypercare | 22 | 422.73 | 9300 | PM (10d), Tech Lead (6d), Mobile (3d), Backend (3d) | Fixed Milestone
Subtotal Professional Services (290 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 33440 | Nov 23, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Core Platform & BMS Staging Integration Gate | 25% | 41800 | Jan 04, 2027 (End Sprint 3) | Due within 14 days of gate approval
Milestone 3 | Mobile App Feature Complete & Wallet NFC Gate | 30% | 50160 | Feb 08, 2027 (End Sprint 6) | Due within 14 days of gate approval
Milestone 4 | Tower 1 Pilot Go-Live & Turnstile Acceptance | 15% | 25080 | Feb 22, 2027 (End Sprint 7) | Due within 14 days of gate approval
Milestone 5 | Portfolio Handover & 60-Day Hypercare Acceptance | 10% | 16720 | Mar 08, 2027 (Final Gate) | Due within 30 days of sign-off