## Overview
PROPOSAL: GLOBAL CLOUD HRM, PAYROLL COMPLIANCE & OKR PLATFORM
Client: TalentoHR Global Enterprise Pty Ltd ¦ Proposal ID: PRP-2026-TLN-09 ¦ Date: 26 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | TalentoHR Global Enterprise Pty Ltd | Presale Solution Lead | Eleanor Vance (Principal HRIS Architect)
Project Code | PBL6-TLN-HRM-2026 | Delivery Manager | Simon Croft (Senior Enterprise Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 07 December 2026
Primary Objective | Implement Unified Cloud HRIS, Multi-Country Payroll Engine, and Mobile Employee Portal | Total Delivery Duration | 20 Calendar Weeks (10 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | TalentoHR risks ATO STP compliance penalties and loses 8 days per cycle due to fragmented multi-country payroll spreadsheets. Lack of mobile self-service frustrates 4,800 employees across 4 countries.
Proposed Strategic Solution | We propose 'TalentoPulse Cloud HRIS': A SOC2-compliant enterprise platform featuring automated ATO STP Phase 2 payroll engine, multi-currency salary disbursements, React Native mobile self-service, and OKR alignment.
Measurable Business Impact | • Payroll processing cycle compressed from 8 business days down to 4 hours. • 100% elimination of ATO STP Phase 2 non-compliance penalty risks. • Employee self-service adoption rate exceeding 94% across all 4 countries. • Manual timesheet reconciliation errors reduced by 99% via geofenced clock-in.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $162,000 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $16,200 | Payment Term Milestone Structure | 5 Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $178,200 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $4,800/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
HRIS & Payroll Solution Architect | Vendor | Part-Time (40%) | Multi-country payroll tax rules, ATO STP Phase 2 architecture, SOC 2 compliance | Architecture Blueprint, Security Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint governance, payroll pilot oversight, executive steering committee reports | Project Plan, Risk Register | Senior
Technical Lead | Vendor | Full-Time (100%) | Ledger integration, calculation engine accuracy, code review governance | Core Codebase, CI/CD Pipeline | Lead
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Payroll calculation engine, timesheet workflows, NetSuite ERP connector | REST/GraphQL APIs, Data Models | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | HR admin web console, performance review matrix, visual OKR hierarchy | Web Console, UI Components | Senior
Senior Mobile Engineer | Vendor | Full-Time (100%) | React Native employee self-service app (iOS/Android) with biometric auth | Mobile Apps (iOS & Android) | Senior
QA / Payroll Audit Lead | Vendor | Full-Time (100%) | Parallel payroll math audits, compliance verification, automated regression | Audit Clearance Report | Senior

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Discrepancy in complex award interpretation (Australia Fair Work Act overtime rules). | High | Low | Conduct 3 parallel pay runs comparing legacy calculations against new engine before go-live. | Payroll Architect
RSK-02 | Risk | ATO Single Touch Payroll gateway certification delays. | Medium | Low | Partner with accredited MessageXchange STP gateway provider with pre-certified ATO connectors. | Tech Lead
DEP-01 | Dependency | Historical payroll and employee master data extract in CSV format by Week 3. | High | Open | Client HR operations team preparing export scripts from legacy software. | Client HR Lead

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-PAY-01 | Payroll Engine | Automated Award Interpretation | System shall calculate base salary, overtime penalties, shift allowances, and superannuation per Fair Work awards. | Must-Have | High | Sprint 2
FR-PAY-02 | Payroll Engine | ATO STP Phase 2 Reporting | System shall generate and lodge cryptographically signed STP Phase 2 pay event JSON directly to ATO gateway. | Must-Have | High | Sprint 3
FR-MOB-01 | Employee App | Mobile Leave & Expense Claims | Employees shall submit leave requests, photograph receipts for expense claims, and view payslips on mobile. | Must-Have | High | Sprint 4
FR-OKR-01 | Performance & OKR | Hierarchical Goal Cascading | System shall link company objectives to department key results and individual goals with quarterly grading. | Should-Have | Medium | Sprint 6
FR-SEC-01 | Security & SSO | Okta / Azure AD SAML 2.0 | System shall enforce SSO and automated role provisioning/deprovisioning via SCIM 2.0 protocol. | Must-Have | Medium | Sprint 5

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
HR Admin Web Console | Next.js 15 (React 19, TypeScript) | 15.0+ | Clean modern web portal with rich data grids, payroll approval dashboards, and charts. | Open Source / AWS | CloudFront CDN
Employee Mobile App | React Native (Expo SDK 52) | 0.76+ | Cross-platform mobile application with biometric FaceID login and push notifications. | Open Source | Encrypted Local Storage
Payroll Engine Service | Node.js (NestJS) & Python | 20.x / 3.12 | NestJS for employee workflows; Python worker for high-precision decimal math calculations. | Open Source / AWS EKS | Auto-scaling Pods (3-12)
Core Database | PostgreSQL (AWS Aurora) | 16.x | ACID compliant relational database with transparent column-level encryption for salary data. | AWS Aurora Multi-AZ | Multi-AZ Failover
Cloud & Compliance | AWS Sydney (ap-southeast-2) | N/A | Complies with Australian Privacy Principles and SOC 2 Type II data security baselines. | AWS Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Payroll Batch Processing Speed | Complete end-to-end payroll calculation for 4,800 employees across 4 countries in < 15 minutes. | Automated stress benchmark with simulated employee ledger. | Multi-threaded Python worker microservices. | Sprint 8
NFR-AVAIL-01 | System Availability | 99.95% system uptime across all business hours. | Datadog synthetic monitoring with automated pod failover. | AWS EKS cluster with multi-AZ Aurora database. | Production Go-Live
NFR-SEC-01 | Salary Privacy & RBAC | Strict role-based encryption ensuring salaries are visible only to authorized HR compensation directors. | Independent SOC 2 compliance penetration test. | Field-level encryption with AWS KMS CMK keys. | Sprint 9

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (20 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & Award Rule Blueprint | Week 1 | 3 Weeks | Payroll rules workshops, award interpretation specification, Figma design system, API specs. | Award Rule Specification, Architecture Blueprint, Figma Design | Milestone 1 Sign-off
Phase 2 | Core Payroll Engine & ATO STP Connector | Week 4 | 6 Weeks | Develop payroll calculation engine, ATO STP Phase 2 gateway integration, NetSuite ledger connector. | Payroll Engine in Staging, Parallel Pay Run 1 Demo | Milestone 2 Sign-off
Phase 3 | Employee Mobile App & Leave/Expense Workflows | Week 10 | 5 Weeks | Develop React Native mobile app, geofenced timesheet clock-in, leave approval matrix. | TestFlight / Play Console Mobile Builds, Self-Service Demo | Milestone 3 Sign-off
Phase 4 | Parallel Pay Runs (3 Cycles) & Security Pentest | Week 15 | 3 Weeks | 3 consecutive live parallel payroll runs, external SOC 2 penetration test, UAT sign-off. | Parallel Pay Audit Sign-off, UAT Acceptance Certificate | Milestone 4 Sign-off
Phase 5 | Production Cutover & Post-Payroll Hypercare | Week 18 | 2 Weeks | Live payroll execution, legacy software decommissioning, 60-day hypercare support. | Production Handover Runbook, Final Acceptance Certificate | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & Award Blueprint | 36 | 625 | 22500 | HRIS Architect (12d), PM (8d), Tech Lead (8d), UI/UX (8d) | Fixed Milestone
WBS-02 | Phase 2: Payroll Engine, STP Gateway & ERP Connector | 120 | 520 | 62400 | Backend (50d), Tech Lead (25d), PM (15d), QA (20d), DevOps (10d) | Fixed Milestone
WBS-03 | Phase 3: Employee Mobile App & Timesheet Workflows | 90 | 516.67 | 46500 | Mobile (45d), Backend (20d), QA (15d), PM (10d) | Fixed Milestone
WBS-04 | Phase 4: 3 Parallel Pay Runs, Pentest & UAT | 42 | 483.33 | 20300 | QA Lead (20d), Payroll Architect (8d), PM (8d), DevOps (6d) | Fixed Milestone
WBS-05 | Phase 5: Production Cutover & Hypercare | 22 | 477.27 | 10500 | Tech Lead (8d), PM (8d), Backend (3d), Mobile (3d) | Fixed Milestone
Subtotal Professional Services (310 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 35640 | Dec 07, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Payroll Engine & Parallel Pay Run 1 Demo | 25% | 44550 | Jan 18, 2027 (End Sprint 3) | Due within 14 days of gate approval
Milestone 3 | Employee Mobile App Feature Complete Gate | 30% | 53460 | Feb 22, 2027 (End Sprint 6) | Due within 14 days of gate approval
Milestone 4 | 3 Parallel Pay Runs Audit & UAT Acceptance | 15% | 26730 | Mar 15, 2027 (End Sprint 8) | Due within 14 days of gate approval
Milestone 5 | Production Payroll Go-Live & Hypercare Gate | 10% | 17820 | Mar 29, 2027 (Final Gate) | Due within 30 days of sign-off