## Overview
PROPOSAL: HYPERLOCAL ON-DEMAND GROCERY & DELIVERY SUPER-APP
Client: QuickDrop Express Australia Pty Ltd ¦ Proposal ID: PRP-2026-QKD-08 ¦ Date: 24 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | QuickDrop Express Australia Pty Ltd | Presale Solution Lead | Dominic Russo (Principal Logistics & App Architect)
Project Code | PBL6-QKD-DELIV-2026 | Delivery Manager | Lucas Meyer (Senior Mobile & Dispatch Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 30 November 2026
Primary Objective | Deploy 3-Sided On-Demand Super-App (Customer, Dark Store Picker, Rider) & Dispatch Engine | Total Delivery Duration | 22 Calendar Weeks (11 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | QuickDrop suffers from order stockouts (6.8%) and courier route delays exceeding 35 minutes due to fragmented systems. High payment processing fees erode ultra-thin retail grocery margins.
Proposed Strategic Solution | We propose 'QuickDrop Nexus': A reactive, high-throughput delivery platform featuring Flutter customer apps, dark store wave-picking tablet UI, AI driver dispatch engine with dynamic batching, and PayID instant rails.
Measurable Business Impact | • Average delivery time compressed from 35 minutes down to < 18 minutes. • Stockout cancellations reduced from 6.8% to < 0.4% via Redis inventory locks. • Picker throughput accelerated to 45 seconds per average 12-item basket. • Payment processing transaction fees reduced by 42% via automated PayID adoption.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $182,000 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $18,200 | Payment Term Milestone Structure | 5 Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $200,200 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $5,000/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
On-Demand Solution Architect | Vendor | Part-Time (40%) | Reactive dispatch engine architecture, Google Maps optimization, payment gateway design | Architecture Blueprint, Routing Algorithm Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint planning, dark store site pilots, budget and milestone governance | Project Plan, Risk Register | Senior
Technical Lead | Vendor | Full-Time (100%) | High-throughput microservices, WebSockets live rider tracking, code quality gates | Core Codebase, CI/CD Pipeline | Lead
Senior Mobile Engineers (3) | Vendor | Full-Time (300%) | Flutter customer app, rider app (background GPS tracking), dark store picker tablet app | 3 Mobile Applications (iOS & Android) | Senior
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Dispatch microservice, dynamic order routing, inventory reservation engine | Microservices, Database Schemas | Senior
QA / Field Testing Lead | Vendor | Full-Time (100%) | Live rider simulation in field, dark store picking stress test, load testing | Test Automation Suites, Field Trial Report | Senior

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Google Maps Route API costs spiking during high-frequency rider GPS polling. | High | Medium | Implement H3 hexagonal spatial indexing and Kalman filter throttling on driver mobile clients. | Tech Lead
RSK-02 | Risk | Rider background geolocation termination on iOS / Android during battery-saver mode. | High | Low | Implement foreground service with persistent notification and native background GPS keep-alive. | Mobile Lead
DEP-01 | Dependency | Zepto PayID commercial payment processing merchant agreement signed by Week 3. | High | Open | Client finance team finalizing underwriting requirements with Zepto. | Client CFO

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-CST-01 | Customer App | Live Basket & Inventory Reservation | App shall reserve items in nearest dark store for 10 minutes upon adding to cart to prevent stockouts. | Must-Have | High | Sprint 1
FR-CST-02 | Customer App | Live Map Rider Telemetry | App shall render live rider motorcycle/bicycle location on Mapbox/Google Maps with dynamic ETA. | Must-Have | High | Sprint 3
FR-PCK-01 | Dark Store Picker | Optimized Path Wave Picking | Picker app shall sort items by shelf aisle coordinates to guide 1-way walking loop through dark store. | Must-Have | High | Sprint 4
FR-RDR-01 | Rider App | Intelligent Order Batching | Dispatch engine shall offer clustered nearby deliveries to single rider when delivery window permits. | Must-Have | High | Sprint 6
FR-PAY-01 | Payments Hub | Instant PayID & 1-Click Apple Pay | Checkout shall support PayID QR/identifier and Apple Pay/Google Pay with instant webhook confirmation. | Must-Have | Medium | Sprint 5

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Customer & Rider Apps | Flutter 3.x (Dart) | 3.24+ | Single high-performance codebase compiling natively to iOS and Android. | Open Source / Native | Redundant App Store CDN
Dispatch Engine | Go (Golang Microservices) | 1.23+ | Sub-10ms response time handling geospatial clustering and linear route optimization. | Open Source / AWS EKS | Auto-scaling Pods (4-25)
Real-Time Geolocation Bus | Redis Enterprise & WebSockets | 7.2+ | In-memory Pub/Sub broadcasting driver coordinates to active customers every 3 seconds. | AWS ElastiCache | Multi-AZ Cluster Mode
Primary Transaction DB | PostgreSQL (AWS Aurora) | 16.x | ACID compliant transactional store for orders, items, pricing, and driver manifests. | AWS Aurora Multi-AZ | Automated Daily Backups
Cloud Infrastructure | AWS Sydney (ap-southeast-2) | N/A | Sub-20ms latency across east coast metropolitan dark store footprint. | AWS Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Dispatch Execution Latency | Automated algorithmic matching and rider assignment triggered within < 2 seconds of order confirmation. | Performance benchmark simulating 1,000 orders/minute. | In-memory Go routing engine with spatial index. | Sprint 10
NFR-AVAIL-01 | System Availability | 99.95% system uptime during dinner peak hours (5:00 PM - 10:00 PM). | Synthetic uptime probes with automated pod self-healing. | Multi-AZ deployment across 3 availability zones. | Production Go-Live
NFR-SEC-01 | PCI-DSS Compliance | Card data tokenized via Stripe Elements; zero cardholder data touches QuickDrop servers. | External QSA vulnerability scan and audit certificate. | Stripe PCI-DSS Level 1 compliance integration. | Sprint 9

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (22 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & UX Design | Week 1 | 3 Weeks | Requirements workshops, dispatch algorithm design, Figma UI systems for 3 apps, API design. | Architecture Document, Interactive Figma Prototypes | Milestone 1 Sign-off
Phase 2 | Core Commerce, Inventory Ledger & Dark Store App | Week 4 | 7 Weeks | Develop real-time inventory ledger, dark store picking app, checkout & PayID integration. | Commerce API Staging Demo, Picker Tablet App Build | Milestone 2 Sign-off
Phase 3 | Customer App, Rider App & Dispatch Engine | Week 11 | 6 Weeks | Develop Flutter customer app, rider mobile app, background GPS tracking, dispatch engine. | TestFlight / Play Console Builds for 3 Apps, Routing Demo | Milestone 3 Sign-off
Phase 4 | Dark Store Pilot Trial, Load Testing & UAT | Week 17 | 3 Weeks | Live pilot at Sydney CBD dark store (500 orders/day), k6 load testing, UAT sign-off. | Pilot Acceptance Certificate, Load Test Sign-off | Milestone 4 Sign-off
Phase 5 | Full Network Cutover (18 Stores) & Hypercare | Week 20 | 3 Weeks | Rollout to all 18 dark stores, rider onboarding training, 90-day hypercare support. | Full Network Handover, Final Acceptance Certificate | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Inception & 3-App UI Design | 40 | 625 | 25000 | Solution Architect (12d), PM (8d), Tech Lead (8d), UI/UX (12d) | Fixed Milestone
WBS-02 | Phase 2: Commerce API, Inventory Locks & Picker App | 125 | 520 | 65000 | Backend (55d), Mobile/Tablet (35d), Tech Lead (15d), QA (20d) | Fixed Milestone
WBS-03 | Phase 3: Customer App, Rider App & Dispatch Engine | 115 | 521.74 | 60000 | Mobile (55d), Backend (30d), QA (20d), PM (10d) | Fixed Milestone
WBS-04 | Phase 4: Dark Store Pilot Trial & Load Testing | 44 | 488.64 | 21500 | QA Lead (20d), Tech Lead (10d), PM (8d), DevOps (6d) | Fixed Milestone
WBS-05 | Phase 5: Network Cutover (18 Stores) & Hypercare | 26 | 411.54 | 10700 | PM (10d), Tech Lead (8d), Mobile (4d), Backend (4d) | Fixed Milestone
Subtotal Professional Services (350 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 40040 | Nov 30, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Commerce API & Dark Store Picker Demo Gate | 25% | 50050 | Jan 18, 2027 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Customer & Rider App Feature Complete Gate | 30% | 60060 | Mar 01, 2027 (End Sprint 7) | Due within 14 days of gate approval
Milestone 4 | Sydney Pilot Acceptance & Load Test Clearance | 15% | 30030 | Mar 22, 2027 (End Sprint 9) | Due within 14 days of gate approval
Milestone 5 | Full Network Launch & 90-Day Hypercare Gate | 10% | 20020 | Apr 12, 2027 (Final Gate) | Due within 30 days of sign-off