## Overview
PROPOSAL: INDUSTRIAL IOT PREDICTIVE MAINTENANCE & TELEMETRY PLATFORM
Client: PrecisionSteel Manufacturing Corporation ¦ Proposal ID: PRP-2026-PCS-10 ¦ Date: 28 October 2026 ¦ Validity: 30 Days
PROJECT METADATA
Client Name | PrecisionSteel Manufacturing Corporation | Presale Solution Lead | Viktor Novak (Principal IIoT & Industry 4.0 Architect)
Project Code | PBL6-PCS-IIOT-2026 | Delivery Manager | Gerard Sullivan (Senior Industrial Tech Delivery Lead)
Proposal Version | v1.0 (Full Technical & Commercial) | Target Kick-off | 14 December 2026
Primary Objective | Deploy Industrial IoT Edge Ingestion, AI Anomaly Detection, and SAP PM Auto-Work Orders | Total Delivery Duration | 24 Calendar Weeks (12 Sprints)
EXECUTIVE SUMMARY & 'WHY THIS SOLUTION'
Executive Problem Context | PrecisionSteel experiences catastrophic gearbox failures costing $220k/incident due to 30-day manual inspection cycles. Critical telemetry remains trapped in isolated plant PLCs with zero predictive warning.
Proposed Strategic Solution | We propose 'SteelPulse Industry 4.0': An edge-to-cloud industrial telemetry platform ingesting continuous OPC-UA/MQTT vibration metrics into AWS IoT Core, running Autoencoder ML anomaly detection to warn of bearing degradation 21 days in advance.
Measurable Business Impact | • Unplanned mill downtime reduced by 68%, saving an estimated $1.2M annually. • Machine failure warning lead time extended from 0 days to 21 days predictive horizon. • Asset maintenance technician productivity increased by 45% via condition-based routing. • Energy consumption reduced by 8.4% by rescheduling heavy rolling passes outside peak tariffs.
COMMERCIAL & INVESTMENT SNAPSHOT (USD)
Core Services Subtotal | $192,000 ex GST | Warranty & Support Period | 90 Calendar Days Hypercare Included
Project Contingency Buffer (10%) | $19,200 | Payment Term Milestone Structure | 5 Milestone Gates (20/25/30/15/10)
Total Delivery Investment | $211,200 ex GST | Ongoing SLA Support (Tier 2/3) | Optional AUD $5,500/month (99.95% Uptime SLA)

## Project Roles
PROJECT ORGANIZATION & TEAM ROLES
Governance structure, resource allocation and RACI matrix.
Role Title | Organization | Allocation | Primary Responsibilities | Key Deliverables Owned | Seniority
IIoT & Industry 4.0 Architect | Vendor | Part-Time (40%) | OPC-UA edge gateway architecture, AWS IoT Core design, IEC 62443 industrial security | Architecture Blueprint, Edge Telemetry Spec | Principal
Project Manager | Vendor | Full-Time (100%) | Sprint governance, plant site safety protocols, SAP PM integration oversight | Project Plan, Risk Register | Senior
Technical Lead | Vendor | Full-Time (100%) | Edge computing runtime, time-series database architecture, code review quality gate | Core Codebase, CI/CD Pipeline | Lead
Senior Data / ML Engineer | Vendor | Full-Time (100%) | Fast Fourier Transform (FFT) feature engineering, unsupervised anomaly detection models | ML Models, Pipeline Specifications | Senior
Senior Backend Engineers (2) | Vendor | Full-Time (200%) | Time-series stream processing, asset hierarchy API, SAP PM bidirectional connector | REST APIs, Ingestion Services | Senior
Senior Frontend Engineer | Vendor | Full-Time (100%) | Next.js asset health dashboard, interactive 3D digital twin viewer, alert console | Web Portals, Telemetry Visuals | Senior
QA / Field Commissioning Lead | Vendor | Full-Time (100%) | Industrial vibration sensor calibration, edge failover testing, load testing | Test Suite, Commissioning Certificate | Senior

## Project Management Approach
PROJECT MANAGEMENT & DELIVERY METHODOLOGY
Agile Scrum framework, ceremonies, quality gates, and communication cadence.
1. AGILE DELIVERY FRAMEWORK & SPRINTS
Sprint Duration | 2 Calendar Weeks per Sprint.
Sprint Planning | Alternate Mondays (9:00 AM - 11:00 AM). User stories estimated via Fibonacci planning poker.
Daily Standup | 15-minute daily sync at 9:30 AM via Slack/Google Meet: Yesterday, Today, Blockers.
Sprint Review & Live Demo | Alternate Fridays (3:00 PM - 4:00 PM). Live functional demonstration in Staging.
Sprint Retrospective | Alternate Fridays (4:00 PM - 5:00 PM). Continuous process improvement and velocity review.
2. TOOLING & COLLABORATION PLATFORMS
Project Management & Backlog | Jira Software – Epics, User Stories, Bug tracking, Sprint Burndown Charts.
Documentation & Knowledge Base | Confluence – Architecture Decision Records (ADRs), API specs, Runbooks.
Version Control & CI/CD | GitHub Enterprise – Trunk-based development, 2 peer approvals per PR, automated tests.
UI/UX Design Collaboration | Figma – Design systems, mobile viewports, click-through interactive prototypes.
Real-Time Communications | Slack – Dedicated shared channels (#project-daily, #project-tech-dev, #project-announcements).
3. QUALITY GOVERNANCE & CODE REVIEW GATES
Code Review Standards | Every PR requires 2 peer approvals (including Tech Lead). Automated linter and formatting checks.
Automated Test Gates | SonarQube scan: 0 critical vulnerabilities, < 3% code duplication, >= 80% unit test coverage.
Deployment Automation | Automated deployment to Dev on merge; automated Staging deployment on sprint release tag.
4. SCOPE CHANGE MANAGEMENT PROCEDURE (CR)
Change Request Trigger | Any requirement deviation exceeding 10% of agreed Functional Requirements baseline.
Impact Assessment | Vendor PM & Architect evaluate budget, timeline, and dependencies within 48 business hours.
Commercial Agreement | Formal Change Order document signed off by Client Sponsor prior to execution.

## RAID
RAID LOG: RISKS, ASSUMPTIONS, ISSUES & DEPENDENCIES
Active risk management matrix monitored continuously.
ID | Category | Item Description | Impact | Probability | Mitigation Strategy & Action Plan | Owner
RSK-01 | Risk | Harsh plant environment (extreme heat, metal dust, electromagnetic interference) degrading sensors. | High | Low | Specify IP68 / ATEX Zone 2 rated industrial vibration transmitters with shielded cabling. | Hardware Lead
RSK-02 | Risk | Industrial OT network firewall restrictions preventing outbound cloud MQTT traffic. | High | Low | Deploy DMZ edge gateway with outbound-only TLS 1.3 mTLS connection to AWS IoT Core. | Security Architect
DEP-01 | Dependency | OPC-UA server tag configuration and access credentials provided by plant SCADA team. | High | Open | Plant automation manager scheduled tag mapping workshop for Week 2. | Client SCADA

## Acceptance Docs
QUALITY ASSURANCE, ACCEPTANCE CRITERIA & DEFECT SLA
Definition of Done (DoD) and production defect severity SLAs.
1. DEFINITION OF DONE (DoD) FOR SPRINT USER STORIES
Criterion 1: Code Review | All code committed to feature branch, passed linter, approved by 2 senior developers via GitHub PR.
Criterion 2: Automated Tests | Unit tests written and passing with >= 80% code coverage. Automated integration tests pass.
Criterion 3: Security & Quality | SonarQube scan passes with 0 Blocker/Critical bugs and 0 high-severity security vulnerabilities.
Criterion 4: Deployment & Config | Code automatically deployed to Staging with database migration scripts verified idempotently.
Criterion 5: Documentation | API documentation generated via OpenAPI/Swagger. Architecture decisions recorded in Confluence.
Criterion 6: Acceptance Sign-off | Client Product Owner verifies story in Staging and marks Jira story 'Accepted'.
2. DEFECT SEVERITY CLASSIFICATION & RESOLUTION SLA (UAT & WARRANTY)
Severity Level | Definition | Example Scenario | Initial Response SLA | Target Resolution SLA | Exit Gate Impact
P1 – Blocker | Critical system outage, total data loss risk, or complete stoppage of core checkout/operations. | Core transaction engine crashes; all user transactions cease. | < 1 Hour | < 4 Hours | Blocks Milestone Go-Live (Zero P1 tolerated)
P2 – Critical | Major feature unusable with no reasonable workaround available for staff or users. | Primary workflow crashes on specific supported browser/device. | < 2 Hours | < 8 Hours | Blocks Milestone Go-Live (Zero P2 tolerated)
P3 – Major | Feature failure but reasonable manual workaround exists without business disruption. | Non-critical notification fails to trigger; alternative channel delivers status. | < 4 Hours | < 24 Hours | Max 3 open P3 allowed with approved fix plan
P4 – Minor | Cosmetic, minor UI alignment issue, or minor typo with zero functional impact. | Dashboard chart legend overlaps slightly on mobile viewport resolution. | < 8 Hours | < 72 Hours | Resolved in subsequent scheduled patch release

## FR
FUNCTIONAL REQUIREMENTS MATRIX (FR)
Detailed functional breakdown across platform modules.
Requirement ID | Functional Module | Feature Name | Detailed User Story & Specification | Priority (MoSCoW) | Complexity | Sprint Allocation
FR-ING-01 | Telemetry Ingestion | Continuous OPC-UA / MQTT Pipeline | System shall ingest 10,000 samples/sec of 3-axis vibration and bearing temperature metrics via edge gateway. | Must-Have | High | Sprint 2
FR-ANM-01 | AI Predictive Engine | Bearing Vibration Spectral Anomaly | System shall compute FFT spectra and trigger early bearing degradation alerts when RMS harmonics exceed ISO 10816 thresholds. | Must-Have | High | Sprint 4
FR-DSH-01 | Asset Dashboard | Asset Health Index & 3D Twin | Executive web portal shall display color-coded asset health index (0-100) across all 4 plants with drill-down vibration graphs. | Must-Have | Medium | Sprint 5
FR-SAP-01 | Enterprise ERP Sync | Automated SAP PM Work Orders | System shall automatically create SAP PM maintenance notifications when critical anomaly persists for > 4 hours. | Must-Have | High | Sprint 7
FR-ALT-01 | Alerting & Escalation | PagerDuty & SMS Dispatch | System shall dispatch critical alarm notifications to on-duty plant engineers with audio spectrogram snapshots. | Must-Have | Medium | Sprint 6

## Tech-stack
TECHNICAL ARCHITECTURE & TECHNOLOGY STACK
Tiered architecture, technology choices, and architectural rationale.
Architecture Tier | Component / Framework | Version | Selection Rationale & Technical Justification | Licensing & Hosting | High Availability
Asset Health Web Portal | Next.js 15 (React 19, TypeScript) | 15.0+ | Real-time canvas-based spectrogram charts, dark mode industrial UI, Tailwind CSS. | Open Source / AWS | CloudFront CDN
Time-Series Database | TimescaleDB / AWS Timestream | N/A | Optimized time-series telemetry storage processing 50M records/day with automatic rollups. | AWS Managed | Multi-AZ Storage
IIoT Edge Gateway | AWS IoT Greengrass & Docker | 2.13+ | On-premise edge computing running local OPC-UA poller and offline data buffering. | AWS Greengrass | Dual Redundant Industrial PCs
Core Asset API | Node.js (NestJS) & Go | 20.x / 1.23 | Modular enterprise API layer managing asset hierarchies, alerts, and user permissions. | Open Source / AWS EKS | Auto-scaling Pods (3-15)
Cloud & Security | AWS Sydney (ap-southeast-2) | N/A | IEC 62443 compliant architecture, VPC private subnets, Hardware Security Module keys. | AWS Enterprise | Multi-AZ (3 Zones)

## Non-FR
NON-FUNCTIONAL REQUIREMENTS (NFR) & ARCHITECTURAL BASELINE
Performance SLAs, system availability, data security, and disaster recovery.
NFR ID | Quality Attribute | Target Metric / Specification | Measurement Methodology | Architecture Enforcement Mechanism | Verification Phase
NFR-PERF-01 | Alert Dispatch Latency | Critical mechanical anomaly detection to PagerDuty alert notification triggered in < 5 seconds. | Automated stress benchmark simulating sudden bearing spike. | Real-time Kafka stream processing. | Sprint 9
NFR-AVAIL-01 | System Availability | 99.95% cloud telemetry uptime across 24/7 continuous casting operations. | Synthetic health probes with automated pod self-healing. | Multi-AZ deployment across 3 availability zones. | Production Go-Live
NFR-SEC-01 | Industrial Cybersecurity | Full adherence to IEC 62443-3-3 OT/IT security standard with zero inbound ports into plant network. | External industrial cybersecurity penetration audit. | mTLS authentication and unidirectional gateway proxy. | Sprint 10

## RateCard
STANDARD PROFESSIONAL SERVICES RATE CARD
Standard hourly and daily rates by seniority and role (USD ex Tax).
Role Title | Seniority Level | Hourly Rate (USD) | Daily Rate (USD) | Weekly Rate (USD) | Typical Experience Profile
Solution Architect | Principal | 87.5 | 700 | 3500 | 12+ yrs enterprise architecture, cloud certified
Project Manager / Scrum Master | Senior | 68.75 | 550 | 2750 | 8+ yrs Agile management, PMP / PMI-ACP
Technical Lead | Lead | 75 | 600 | 3000 | 10+ yrs distributed systems, code quality governance
Senior Backend Engineer | Senior | 60 | 480 | 2400 | 6+ yrs microservices, database performance, APIs
Senior Frontend Engineer | Senior | 57.5 | 460 | 2300 | 6+ yrs modern React, SSR, UI/UX implementation
Senior Mobile Engineer | Senior | 60 | 480 | 2400 | 6+ yrs native & Flutter, offline sync, hardware APIs
QA / Automation Test Lead | Senior | 50 | 400 | 2000 | 7+ yrs test automation, Cypress, load testing
UI/UX Product Designer | Senior | 52.5 | 420 | 2100 | 7+ yrs enterprise design systems, usability testing
DevOps / Cloud Engineer | Senior | 65 | 520 | 2600 | 6+ yrs AWS/GCP, Kubernetes, Terraform IaC
Business Analyst | Senior | 55 | 440 | 2200 | 6+ yrs domain workflows, specification sign-off
Security & Compliance Specialist | Lead | 85 | 680 | 3400 | 10+ yrs cybersecurity, SOC2/PCI/HIPAA audit

## Macro Plan & Quotation
MACRO IMPLEMENTATION PLAN & DETAILED COMMERCIAL QUOTATION
Phased timeline, Work Breakdown Structure (WBS), Quotation, and Milestone Gates.
1. PHASED MACRO ROADMAP & DELIVERABLE MILESTONES (24 WEEKS)
Phase # | Phase Name & Objective | Start (Wk) | Duration | Key Activities & Milestones | Primary Deliverables | Gate Sign-off
Phase 1 | Inception, Architecture & Plant Survey | Week 1 | 3 Weeks | Site visits to 4 plants, OPC-UA tag survey, edge gateway hardware specification, Figma UI design. | Site Audit Report, Architecture Blueprint, Figma Prototype | Milestone 1 Sign-off
Phase 2 | Edge Gateway Deployment & Ingestion Pipeline | Week 4 | 7 Weeks | Deploy AWS Greengrass edge PCs at Newcastle plant, develop OPC-UA poller, TimescaleDB setup. | Live Telemetry Pipeline in Staging, Edge Gateway Build | Milestone 2 Sign-off
Phase 3 | AI Predictive Engine, Web Portal & SAP PM Sync | Week 11 | 7 Weeks | Develop FFT spectral anomaly model, web health dashboard, automated SAP PM work order integration. | Asset Health Portal Demo, SAP PM Connector Test | Milestone 3 Sign-off
Phase 4 | Pilot Machine Validation (Newcastle Plant) & Load Test | Week 18 | 3 Weeks | Live validation on 50 critical rolling mill assets, vibration calibration, k6 load test. | Pilot Acceptance Certificate, Vibration Accuracy Report | Milestone 4 Sign-off
Phase 5 | Full Rollout (All 4 Plants) & 90-Day Hypercare | Week 21 | 3 Weeks | Deploy remaining 400 assets across 3 plants, plant maintenance staff training, hypercare. | Full Plant Acceptance Sign-off, Final Handover | Final Milestone 5 Gate
2. WORK BREAKDOWN STRUCTURE (WBS) & EFFORT ESTIMATION
WBS ID | Deliverable Component | Est. Man-Days | Blended Day Rate | Subtotal (USD) | Resource Composition | Billing Type
WBS-01 | Phase 1: Architecture, Site Survey & UI/UX Design | 40 | 650 | 26000 | IIoT Architect (12d), PM (8d), Tech Lead (10d), UI/UX (10d) | Fixed Milestone
WBS-02 | Phase 2: Edge Gateway Deployment & Ingestion Engine | 130 | 523.08 | 68000 | Backend (55d), Tech Lead (25d), IoT Eng (25d), QA (15d), PM (10d) | Fixed Milestone
WBS-03 | Phase 3: AI Predictive Models, Web Portal & SAP Sync | 115 | 521.74 | 60000 | ML Eng (35d), Frontend (30d), Backend (25d), QA (15d), PM (10d) | Fixed Milestone
WBS-04 | Phase 4: Pilot Machine Validation & Calibration | 45 | 488.89 | 22000 | QA/Commissioning (20d), Tech Lead (10d), ML Eng (10d), PM (5d) | Fixed Milestone
WBS-05 | Phase 5: Full Rollout (4 Plants) & Hypercare | 30 | 506.67 | 15200 | Tech Lead (10d), PM (10d), Backend (5d), ML Eng (5d) | Fixed Milestone
Subtotal Professional Services (360 Man-Days)
Project Delivery Contingency Buffer (10%)
TOTAL DELIVERY QUOTATION (USD ex GST/Tax)
3. DELIVERABLE-BASED MILESTONE PAYMENT SCHEDULE
Milestone # | Payment Trigger & Deliverable Gate | % Allocation | Amount (USD) | Project Target Date | Invoice Terms
Milestone 1 | Contract Execution & Architecture Sign-off | 20% | 42240 | Dec 14, 2026 (Kick-off) | Due within 14 days of invoice
Milestone 2 | Edge Gateway Ingestion Pipeline Demo Gate | 25% | 52800 | Feb 01, 2027 (End Sprint 4) | Due within 14 days of gate approval
Milestone 3 | Asset Portal & AI Anomaly Model Demo Gate | 30% | 63360 | Mar 22, 2027 (End Sprint 7) | Due within 14 days of gate approval
Milestone 4 | Newcastle Pilot Sign-off & SAP PM Live Gate | 15% | 31680 | Apr 12, 2027 (End Sprint 9) | Due within 14 days of gate approval
Milestone 5 | Full 4-Plant Network Handover & Hypercare Gate | 10% | 21120 | May 03, 2027 (Final Gate) | Due within 30 days of sign-off